## Summary
Functional group | TC-ID | Total | OK | NG | NT
Operator Login Screen | IT-F-X-X-X | 109 | 0 | 0 | 0 | ※2 browsers
Seatmap Screen | IT-SS-X-X-X | 110 | 52 | 0 | 0 | ※2 browsers
Seatmap License | IT-SL-X-X-X | 7 | 0 | 0 | 0
Wallboard License | IT-WL-X-X-X | 4 | 0 | 0 | 0
Total |  | 449 | 104 | 0 | 0
18-Apr: Hung Kings' Commemoration Day
|  |  |  | 2024-04-11 | 2024-04-12 | 2024-04-13 | 2024-04-14 | 2024-04-15 | 2024-04-16 | 2024-04-17 | 2024-04-18 | 2024-04-19 | 2024-04-20 | 2024-04-21 | 2024-04-22
完了項目数（予定） |  |  |  | 90 | 75 | 0 | 0 | 75 | 75 | 60 | 0 | 58 | 0 | 0 | 0
完了項目数累計（予定） |  |  |  | 90 | 165 | 165 | 165 | 240 | 315 | 375 | 375 | 433 | 433 | 433 | 433
進捗率（予定） |  |  |  | 20.04% | 36.75% | 36.75% | 36.75% | 53.45% | 70.16% | 83.52% | 83.52% | 96.44% | 96.44% | 96.44% | 96.44%
完了項目数累計（実績） |  |  |  | 104 | 104 | 104 | 104 | 104 | 104 | 104 | 104 | 104 | 104 | 104 | 104
進捗率（実績） |  |  |  | 23.16% | 23.16% | 23.16% | 23.16% | 23.16% | 23.16% | 23.16% | 23.16% | 23.16% | 23.16% | 23.16% | 23.16%
残項目数 |  |  |  | 345 | 345 | 345 | 345 | 345 | 345 | 345 | 345 | 345 | 345 | 345 | 345
遅れ(+が遅れ数） |  |  |  | -14 | 61 | 61 | 61 | 136 | 211 | 271 | 271 | 329 | 329 | 329 | 329
Effort | 100% | 100% | 50% | 2024-04-11: 100%
sheet | Duc Huy | Tien Tran | Cuong Bui | 2024-04-11: Hoang Nguyen
Total | 57 | 63 | 104 | 2024-04-11: 58
Operator Login Screen | 57 | 52 | 0 | 2024-04-11: 0
OK | 0 | 0 | 0 | 2024-04-11: 0
NG | 0 | 0 | 0 | 2024-04-11: 0
NT | 0 | 0 | 0 | 2024-04-11: 0
Seatmap Screen | 0 | 0 | 52 | 2024-04-11: 58
OK | 0 | 0 | 52 | 2024-04-11: 0
NG | 0 | 0 | 0 | 2024-04-11: 0
NT | 0 | 0 | 0 | 2024-04-11: 0
Seatmap License | 0 | 7 | 0 | 2024-04-11: 0
OK
NG
NT
Wallboard License | 0 | 4 | 0 | 2024-04-11: 0
OK
NG
NT

## Operator Login Screen
[12 empty] | Number of test items | 109 | OK | 0
[12 empty] | Not implemented | 109 | NG | 0
[12 empty] | Progress rate | 0% | NT | 0
工程 | ＮＯ | Test items | [5 empty] | Preconditions | Steps | Expected Results | 試験実施 有無 | Browser type | Test member | Test day | Test results | Questionnaire number | Retest member | Retest date | Retest result | Finished Day | Remarks
|  | Main category |  | Sub-category |  | Test Title
IT | IT-F-1-1-1 | 1 | Selection | 1 | Display | 1 | Confirm location list with specified layout | 1. The following FreeSeat has been set on seatmap ・Site Name: FreeSeatSettingTest ・Layout: FreeSeat Layout ・Location: - FreeSeat1 - FreeSeat2 | 1. Access Operator login screen | 1.1/ Location number list is follow - FreeSeatSettingTest > FreeSeat Layout > FreeSeat1 - FreeSeatSettingTest > FreeSeat Layout > FreeSeat2 | ○ |  | Tien Tran
IT | IT-F-1-1-2 | 1 |  | 1 |  | 2 | Confirm location list with all layout | 1. The following FreeSeat has been set on seatmap ・Site Name: FreeSeatSettingTest ・Layout: FreeSeat Layout ・Location: - FreeSeat1 - FreeSeat2 ・Site Name: FreeSeatSettingTest ・Layout: FreeSeat Layout2 ・Location: - FreeSeat1 | 1. Access Operator login screen | 1.1/ Location number list is follow - FreeSeatSettingTest > FreeSeat Layout > FreeSeat1 - FreeSeatSettingTest > All layouts > FreeSeat1 - FreeSeatSettingTest > FreeSeat Layout > FreeSeat2 - FreeSeatSettingTest > FreeSeat Layout2 > FreeSeat1 | ○ |  | Tien Tran
IT | IT-F-1-1-3 | 1 |  | 1 |  | 3 | Confirm location list with different site name | 1. The following FreeSeat has been set on seatmap ・Site Name: FreeSeatSettingTest ・Layout: FreeSeat Layout ・Location: - FreeSeat1 - FreeSeat2 ・Site Name: FreeSeatSettingTest1 ・Layout: FreeSeat Layout ・Location: - FreeSeat1 - FreeSeat2 | 1. Access Operator login screen | 1.1/ Location number list is follow - FreeSeatSettingTest > FreeSeat Layout > FreeSeat1 - FreeSeatSettingTest > FreeSeat Layout > FreeSeat2 - FreeSeatSettingTest1 > FreeSeat Layout > FreeSeat1 - FreeSeatSettingTest1 > FreeSeat Layout > FreeSeat2 | ○ |  | Tien Tran
IT | IT-F-1-2-1 | 1 |  | 2 | Suggest search | 1 | Confirm location list is filtered by search key | 1. The following FreeSeat has been set on seatmap ・Site Name: FreeSeatSettingTest ・Layout: FreeSeat Layout ・Location: - FreeSeat1 - FreeSeat2 ・Site Name: FreeSeatSettingTest ・Layout: FreeSeat Layout2 ・Location: - FreeSeat1 ・Site Name: FreeSeatSettingTest1 ・Layout: FreeSeat Layout ・Location: - FreeSeat1 - FreeSeat2 | 1. Access Operator login screen 2. Enter "seat1" Suggest search of location selection | 1.1/ Location number list is follow - FreeSeatSettingTest > FreeSeat Layout > FreeSeat1 - FreeSeatSettingTest > FreeSeat Layout2 > FreeSeat1 - FreeSeatSettingTest > All layouts > FreeSeat1 - FreeSeatSettingTest1 > FreeSeat Layout > FreeSeat1 | ○ |  | Tien Tran
IT | IT-F-2-1-1 | 2 | Free seat login | 1 | Operator Client Login Screen - Supervisor account | 1 | Pattern No 1 | 1. Site Name, Layout, Location following pattern No 1 ( フリーシートユースケース sheet ) 2. OP and Account Supervisor are in the same Group that have layout in pattern | 1. Access Operator login screen 2. Login into seat follow pattern no 1 ( フリーシートユースケース sheet ) 3.On Seatmap Screen Logged in successfully by using Supervisor account | 3.1/ Seat login is refected follow pattern no 1 ( フリーシートユースケース sheet ) | ○ |  | Tien Tran
IT | IT-F-2-1-2 | 2 |  | 1 |  | 2 | Pattern No 2 | 1. Site Name, Layout, Location following pattern No 2 ( フリーシートユースケース sheet ) 2. OP and Account Supervisor are in the same Group that have layout in pattern | 1. Access Operator login screen 2. Login into seat follow pattern no 2 ( フリーシートユースケース sheet ) 3.On Seatmap Screen Logged in successfully by using Supervisor account | 3.1/ Seat login is refected follow pattern no 2 ( フリーシートユースケース sheet ) | ○ |  | Tien Tran
IT | IT-F-2-1-3 | 2 |  | 1 |  | 3 | Pattern No 3 | 1. Site Name, Layout, Location following pattern No 3 ( フリーシートユースケース sheet ) 2. OP and Account Supervisor are in the same Group that have layout in pattern | 1. Access Operator login screen 2. Login into seat follow pattern no 3 ( フリーシートユースケース sheet ) 3.On Seatmap Screen Logged in successfully by using Supervisor account | 3.1/ Seat login is refected follow pattern no 3 ( フリーシートユースケース sheet ) | ○ |  | Tien Tran
IT | IT-F-2-1-4 | 2 |  | 1 |  | 4 | Pattern No 4 | 1. Site Name, Layout, Location following pattern No 4 ( フリーシートユースケース sheet ) 2. OP and Account Supervisor are in the same Group that have layout in pattern | 1. Access Operator login screen 2. Login into seat follow pattern no 4 ( フリーシートユースケース sheet ) 3.On Seatmap Screen Logged in successfully by using Supervisor account | 3.1/ Seat login is refected follow pattern no 4 ( フリーシートユースケース sheet ) | ○ |  | Tien Tran
IT | IT-F-2-1-5 | 2 |  | 1 |  | 5 | Pattern No 5 | 1. Site Name, Layout, Location following pattern No 5 ( フリーシートユースケース sheet ) 2. OP and Account Supervisor are in the same Group that have layout in pattern | 1. Access Operator login screen 2. Login into seat follow pattern no 5 ( フリーシートユースケース sheet ) 3.On Seatmap Screen Logged in successfully by using Supervisor account | 3.1/ Seat login is refected follow pattern no 5 ( フリーシートユースケース sheet ) | ○ |  | Tien Tran
IT | IT-F-2-1-6 | 2 |  | 1 |  | 6 | Pattern No 6 | 1. Site Name, Layout, Location following pattern No 6 ( フリーシートユースケース sheet ) 2. OP and Account Supervisor are in the same Group that have layout in pattern | 1. Access Operator login screen 2. Login into seat follow pattern no 6( フリーシートユースケース sheet ) 3.On Seatmap Screen Logged in successfully by using Supervisor account | 3.1/ Seat login is refected follow pattern no 6 ( フリーシートユースケース sheet ) | ○ |  | Tien Tran
IT | IT-F-2-1-7 | 2 |  | 1 |  | 7 | Pattern No 7 | 1. Site Name, Layout, Location following pattern No 7 ( フリーシートユースケース sheet ) 2. OP and Account Supervisor are not in the same Group that have layout in pattern | 1. Access Operator login screen 2. Login into seat follow pattern no 7 ( フリーシートユースケース sheet ) 3.On Seatmap Screen Logged in successfully by using Supervisor account | 3.1/ Seat login is refected follow pattern no 7 ( フリーシートユースケース sheet ) | ○ |  | Tien Tran
IT | IT-F-2-1-8 | 2 |  | 1 |  | 8 | Pattern No 8 | 1. Site Name, Layout, Location following pattern No 8 ( フリーシートユースケース sheet ) 2. OP and Account Supervisor are not in the same Group that have layout in pattern | 1. Access Operator login screen 2. Login into seat follow pattern no 8 ( フリーシートユースケース sheet ) 3.On Seatmap Screen Logged in successfully by using Supervisor account | 3.1/ Seat login is refected follow pattern no 8 ( フリーシートユースケース sheet ) | ○ |  | Tien Tran
IT | IT-F-2-1-9 | 2 |  | 1 |  | 9 | Pattern No 9 | 1. Site Name, Layout, Location following pattern No 9 ( フリーシートユースケース sheet ) 2. OP and Account Supervisor are not in the same Group that have layout in pattern | 1. Access Operator login screen 2. Login into seat follow pattern no 9 ( フリーシートユースケース sheet ) 3.On Seatmap Screen Logged in successfully by using Supervisor account | 3.1/ Seat login is refected follow pattern no 9( フリーシートユースケース sheet ) | ○ |  | Tien Tran
IT | IT-F-2-1-10 | 2 |  | 1 |  | 10 | Pattern No 10 | 1. Site Name, Layout, Location following pattern No 10 ( フリーシートユースケース sheet ) 2. OP and Account Supervisor are not in the same Group that have layout in pattern | 1. Access Operator login screen 2. Login into seat follow pattern no 10 ( フリーシートユースケース sheet ) 3.On Seatmap Screen Logged in successfully by using Supervisor account | 3.1/ Seat login is refected follow pattern no 10 ( フリーシートユースケース sheet ) | ○ |  | Tien Tran
IT | IT-F-2-1-11 | 2 |  | 1 |  | 11 | Pattern No 11 | 1. Site Name, Layout, Location following pattern No 11 ( フリーシートユースケース sheet ) 2. OP and Account Supervisor are not in the same Group that have layout in pattern | 1. Access Operator login screen 2. Login into seat follow pattern no 11 ( フリーシートユースケース sheet ) 3.On Seatmap Screen Logged in successfully by using Supervisor account | 3.1/ Seat login is refected follow pattern no 11 ( フリーシートユースケース sheet ) | ○ |  | Tien Tran
IT | IT-F-2-1-12 | 2 |  | 1 |  | 12 | Pattern No 12 | 1. Site Name, Layout, Location following pattern No 12 ( フリーシートユースケース sheet ) 2. OP and Account Supervisor are not in the same Group that have layout in pattern | 1. Access Operator login screen 2. Login into seat follow pattern no 12 ( フリーシートユースケース sheet ) 3.On Seatmap Screen Logged in successfully by using Supervisor account | 3.1/ Seat login is refected follow pattern no 12 ( フリーシートユースケース sheet ) | ○ |  | Tien Tran
IT | IT-F-2-1-13 | 2 |  | 1 |  | 13 | Pattern No 13 | 1. Site Name, Layout, Location following pattern No 13 ( フリーシートユースケース sheet ) 2. OP and Account Supervisor in the same Group that have layout in pattern | 1. Access Operator login screen 2. Login into seat follow pattern no 13 ( フリーシートユースケース sheet ) 3.On Seatmap Screen Logged in successfully by using Supervisor account | 3.1/ Seat login is refected follow pattern no 13 ( フリーシートユースケース sheet ) | ○ |  | Tien Tran
IT | IT-F-2-1-14 | 2 |  | 1 |  | 14 | Pattern No 14 | 1. Site Name, Layout, Location following pattern No 14 ( フリーシートユースケース sheet ) 2. OP and Account Supervisor in the same Group that have layout in pattern | 1. Access Operator login screen 2. Login into seat follow pattern no 14 ( フリーシートユースケース sheet ) 3.On Seatmap Screen Logged in successfully by using Supervisor account | 3.1/ Seat login is refected follow pattern no 14 ( フリーシートユースケース sheet ) | ○ |  | Tien Tran
IT | IT-F-2-1-15 | 2 |  | 1 |  | 15 | Pattern No 15 | 1. Site Name, Layout, Location following pattern No 15 ( フリーシートユースケース sheet ) 2. OP and Account Supervisor in the same Group that have layout in pattern | 1. Access Operator login screen 2. Login into seat follow pattern no 15 ( フリーシートユースケース sheet ) 3.On Seatmap Screen Logged in successfully by using Supervisor account | 3.1/ Seat login is refected follow pattern no 15 ( フリーシートユースケース sheet ) | ○ |  | Tien Tran
IT | IT-F-2-1-16 | 2 |  | 1 |  | 16 | Pattern No 16 | 1. Site Name, Layout, Location following pattern No 16 ( フリーシートユースケース sheet ) 2. OP and Account Supervisor in the same Group that have layout in pattern | 1. Access Operator login screen 2. Login into seat follow pattern no 16 ( フリーシートユースケース sheet ) 3.On Seatmap Screen Logged in successfully by using Supervisor account | 3.1/ Seat login is refected follow pattern no 16 ( フリーシートユースケース sheet ) | ○ |  | Tien Tran
IT | IT-F-2-1-17 | 2 |  | 1 |  | 17 | Pattern No 17 | 1. Site Name, Layout, Location following pattern No 17 ( フリーシートユースケース sheet ) 2. OP and Account Supervisor in the same Group that have layout in pattern | 1. Access Operator login screen 2. Login into seat follow pattern no 17 ( フリーシートユースケース sheet ) 3.On Seatmap Screen Logged in successfully by using Supervisor account | 3.1/ Seat login is refected follow pattern no 17 ( フリーシートユースケース sheet ) | ○ |  | Tien Tran
IT | IT-F-2-1-18 | 2 |  | 1 |  | 18 | Pattern No 18 | 1. Site Name, Layout, Location following pattern No 18 ( フリーシートユースケース sheet ) 2. OP and Account Supervisor in the same Group that have layout in pattern | 1. Access Operator login screen 2. Login into seat follow pattern no 18 ( フリーシートユースケース sheet ) 3.On Seatmap Screen Logged in successfully by using Supervisor account | 3.1/ Seat login is refected follow pattern no 18 ( フリーシートユースケース sheet ) | ○ |  | Tien Tran
IT | IT-F-2-1-19 | 2 |  | 1 |  | 19 | Pattern No 19 | 1. Site Name, Layout, Location following pattern No 19 ( フリーシートユースケース sheet ) 2. OP and Account Supervisor are not in the same Group that have layout in pattern | 1. Access Operator login screen 2. Login into seat follow pattern no 19 ( フリーシートユースケース sheet ) 3.On Seatmap Screen Logged in successfully by using Supervisor account | 3.1/ Seat login is refected follow pattern no 19 ( フリーシートユースケース sheet ) | ○ |  | Tien Tran
IT | IT-F-2-1-20 | 2 |  | 1 |  | 20 | Pattern No 20 | 1. Site Name, Layout, Location following pattern No 20 ( フリーシートユースケース sheet ) 2. OP and Account Supervisor are not in the same Group that have layout in pattern | 1. Access Operator login screen 2. Login into seat follow pattern no 20 ( フリーシートユースケース sheet ) 3.On Seatmap Screen Logged in successfully by using Supervisor account | 3.1/ Seat login is refected follow pattern no 20 ( フリーシートユースケース sheet ) | ○ |  | Tien Tran
IT | IT-F-2-1-21 | 2 |  | 1 |  | 21 | Pattern No 21 | 1. Site Name, Layout, Location following pattern No 21 ( フリーシートユースケース sheet ) 2. OP and Account Supervisor are not in the same Group that have layout in pattern | 1. Access Operator login screen 2. Login into seat follow pattern no 21 ( フリーシートユースケース sheet ) 3.On Seatmap Screen Logged in successfully by using Supervisor account | 3.1/ Seat login is refected follow pattern no 21 ( フリーシートユースケース sheet ) | ○ |  | Tien Tran
IT | IT-F-2-1-22 | 2 |  | 1 |  | 22 | Pattern No 22 | 1. Site Name, Layout, Location following pattern No 22 ( フリーシートユースケース sheet ) 2. OP and Account Supervisor are not in the same Group that have layout in pattern | 1. Access Operator login screen 2. Login into seat follow pattern no 22 ( フリーシートユースケース sheet ) 3.On Seatmap Screen Logged in successfully by using Supervisor account | 3.1/ Seat login is refected follow pattern no 22 ( フリーシートユースケース sheet ) | ○ |  | Tien Tran
IT | IT-F-2-1-23 | 2 |  | 1 |  | 23 | Pattern No 23 | 1. Site Name, Layout, Location following pattern No 23 ( フリーシートユースケース sheet ) 2. OP and Account Supervisor are not in the same Group that have layout in pattern | 1. Access Operator login screen 2. Login into seat follow pattern no 23 ( フリーシートユースケース sheet ) 3.On Seatmap Screen Logged in successfully by using Supervisor account | 3.1/ Seat login is refected follow pattern no 23 ( フリーシートユースケース sheet ) | ○ |  | Tien Tran
IT | IT-F-2-1-24 | 2 |  | 1 |  | 24 | Pattern No 24 | 1. Site Name, Layout, Location following pattern No 24 ( フリーシートユースケース sheet ) 2. OP and Account Supervisor are not in the same Group that have layout in pattern | 1. Access Operator login screen 2. Login into seat follow pattern no 24 ( フリーシートユースケース sheet ) 3.On Seatmap Screen Logged in successfully by using Supervisor account | 3.1/ Seat login is refected follow pattern no 24 ( フリーシートユースケース sheet ) | ○ |  | Tien Tran
IT | IT-F-2-2-1 | 2 |  | 2 | Operator Client Login Screen - Manager account (view mode) | 1 | Pattern No 1 | 1. Site Name, Layout, Location following pattern No 1 ( フリーシートユースケース sheet ) 2. OP and Account Manager are in the same Group that have layout in pattern | 1. Access Operator login screen 2. Login into seat follow pattern no 1 ( フリーシートユースケース sheet ) 3.On Seatmap Screen Logged in successfully by using Manager account ( View Mode ) | 3.1/ Seat login is refected follow pattern no 1 ( フリーシートユースケース sheet ) | ○ |  | Tien Tran
IT | IT-F-2-2-2 | 2 |  | 2 |  | 2 | Pattern No 2 | 1. Site Name, Layout, Location following pattern No 2 ( フリーシートユースケース sheet ) 2. OP and Account Manager are in the same Group that have layout in pattern | 1. Access Operator login screen 2. Login into seat follow pattern no 2 ( フリーシートユースケース sheet ) 3.On Seatmap Screen Logged in successfully by using Manager account ( View Mode ) | 3.1/ Seat login is refected follow pattern no 2 ( フリーシートユースケース sheet ) | ○ |  | Tien Tran
IT | IT-F-2-2-3 | 2 |  | 2 |  | 3 | Pattern No 3 | 1. Site Name, Layout, Location following pattern No 3 ( フリーシートユースケース sheet ) 2. OP and Account Manager are in the same Group that have layout in pattern | 1. Access Operator login screen 2. Login into seat follow pattern no 3 ( フリーシートユースケース sheet ) 3.On Seatmap Screen Logged in successfully by using Manager account ( View Mode ) | 3.1/ Seat login is refected follow pattern no 3 ( フリーシートユースケース sheet ) | ○ |  | Tien Tran
IT | IT-F-2-2-4 | 2 |  | 2 |  | 4 | Pattern No 4 | 1. Site Name, Layout, Location following pattern No 4 ( フリーシートユースケース sheet ) 2. OP and Account Manager are in the same Group that have layout in pattern | 1. Access Operator login screen 2. Login into seat follow pattern no 4 ( フリーシートユースケース sheet ) 3.On Seatmap Screen Logged in successfully by using Manager account ( View Mode ) | 3.1/ Seat login is refected follow pattern no 4 ( フリーシートユースケース sheet ) | ○ |  | Tien Tran
IT | IT-F-2-2-5 | 2 |  | 2 |  | 5 | Pattern No 5 | 1. Site Name, Layout, Location following pattern No 5 ( フリーシートユースケース sheet ) 2. OP and Account Manager are in the same Group that have layout in pattern | 1. Access Operator login screen 2. Login into seat follow pattern no 5 ( フリーシートユースケース sheet ) 3.On Seatmap Screen Logged in successfully by using Manager account ( View Mode ) | 3.1/ Seat login is refected follow pattern no 5 ( フリーシートユースケース sheet ) | ○ |  | Tien Tran
IT | IT-F-2-2-6 | 2 |  | 2 |  | 6 | Pattern No 6 | 1. Site Name, Layout, Location following pattern No 6 ( フリーシートユースケース sheet ) 2. OP and Account Manager are in the same Group that have layout in pattern | 1. Access Operator login screen 2. Login into seat follow pattern no 6 ( フリーシートユースケース sheet ) 3.On Seatmap Screen Logged in successfully by using Manager account ( View Mode ) | 3.1/ Seat login is refected follow pattern no 6 ( フリーシートユースケース sheet ) | ○ |  | Tien Tran
IT | IT-F-2-2-7 | 2 |  | 2 |  | 7 | Pattern No 7 | 1. Site Name, Layout, Location following pattern No 7 ( フリーシートユースケース sheet ) 2. OP and Account Manager are in the same Group that have layout in pattern | 1. Access Operator login screen 2. Login into seat follow pattern no 7 ( フリーシートユースケース sheet ) 3.On Seatmap Screen Logged in successfully by using Manager account ( View Mode ) | 3.1/ Seat login is refected follow pattern no 7 ( フリーシートユースケース sheet ) | ○ |  | Tien Tran
IT | IT-F-2-2-8 | 2 |  | 2 |  | 8 | Pattern No 8 | 1. Site Name, Layout, Location following pattern No 8 ( フリーシートユースケース sheet ) 2. OP and Account Manager are in the same Group that have layout in pattern | 1. Access Operator login screen 2. Login into seat follow pattern no 8 ( フリーシートユースケース sheet ) 3.On Seatmap Screen Logged in successfully by using Manager account ( View Mode ) | 3.1/ Seat login is refected follow pattern no 8 ( フリーシートユースケース sheet ) | ○ |  | Tien Tran
IT | IT-F-2-2-9 | 2 |  | 2 |  | 9 | Pattern No 9 | 1. Site Name, Layout, Location following pattern No 9 ( フリーシートユースケース sheet ) 2. OP and Account Manager are in the same Group that have layout in pattern | 1. Access Operator login screen 2. Login into seat follow pattern no 9 ( フリーシートユースケース sheet ) 3.On Seatmap Screen Logged in successfully by using Manager account ( View Mode ) | 3.1/ Seat login is refected follow pattern no 9( フリーシートユースケース sheet ) | ○ |  | Tien Tran
IT | IT-F-2-2-10 | 2 |  | 2 |  | 10 | Pattern No 10 | 1. Site Name, Layout, Location following pattern No 10 ( フリーシートユースケース sheet ) 2. OP and Account Manager are in the same Group that have layout in pattern | 1. Access Operator login screen 2. Login into seat follow pattern no 10 ( フリーシートユースケース sheet ) 3.On Seatmap Screen Logged in successfully by using Manager account ( View Mode ) | 3.1/ Seat login is refected follow pattern no 10 ( フリーシートユースケース sheet ) | ○ |  | Tien Tran
IT | IT-F-2-2-11 | 2 |  | 2 |  | 11 | Pattern No 11 | 1. Site Name, Layout, Location following pattern No 11 ( フリーシートユースケース sheet ) 2. OP and Account Manager are in the same Group that have layout in pattern | 1. Access Operator login screen 2. Login into seat follow pattern no 11 ( フリーシートユースケース sheet ) 3.On Seatmap Screen Logged in successfully by using Manager account ( View Mode ) | 3.1/ Seat login is refected follow pattern no 11 ( フリーシートユースケース sheet ) | ○ |  | Tien Tran
IT | IT-F-2-2-12 | 2 |  | 2 |  | 12 | Pattern No 12 | 1. Site Name, Layout, Location following pattern No 12 ( フリーシートユースケース sheet ) 2. OP and Account Manager are in the same Group that have layout in pattern | 1. Access Operator login screen 2. Login into seat follow pattern no 12 ( フリーシートユースケース sheet ) 3.On Seatmap Screen Logged in successfully by using Manager account ( View Mode ) | 3.1/ Seat login is refected follow pattern no 12 ( フリーシートユースケース sheet ) | ○ |  | Tien Tran
IT | IT-F-2-2-13 | 2 |  | 2 |  | 13 | Pattern No 13 | 1. Site Name, Layout, Location following pattern No 13 ( フリーシートユースケース sheet ) 2. OP and Account Manager are in the same Group that have layout in pattern | 1. Access Operator login screen 2. Login into seat follow pattern no 13 ( フリーシートユースケース sheet ) 3.On Seatmap Screen Logged in successfully by using Manager account ( View Mode ) | 3.1/ Seat login is refected follow pattern no 13 ( フリーシートユースケース sheet ) | ○ |  | Tien Tran
IT | IT-F-2-2-14 | 2 |  | 2 |  | 14 | Pattern No 14 | 1. Site Name, Layout, Location following pattern No 14 ( フリーシートユースケース sheet ) 2. OP and Account Manager are in the same Group that have layout in pattern | 1. Access Operator login screen 2. Login into seat follow pattern no 14 ( フリーシートユースケース sheet ) 3.On Seatmap Screen Logged in successfully by using Manager account ( View Mode ) | 3.1/ Seat login is refected follow pattern no 14 ( フリーシートユースケース sheet ) | ○ |  | Tien Tran
IT | IT-F-2-2-15 | 2 |  | 2 |  | 15 | Pattern No 15 | 1. Site Name, Layout, Location following pattern No 15 ( フリーシートユースケース sheet ) 2. OP and Account Manager are in the same Group that have layout in pattern | 1. Access Operator login screen 2. Login into seat follow pattern no 15 ( フリーシートユースケース sheet ) 3.On Seatmap Screen Logged in successfully by using Manager account ( View Mode ) | 3.1/ Seat login is refected follow pattern no 15 ( フリーシートユースケース sheet ) | ○ |  | Tien Tran
IT | IT-F-2-2-16 | 2 |  | 2 |  | 16 | Pattern No 16 | 1. Site Name, Layout, Location following pattern No 16 ( フリーシートユースケース sheet ) 2. OP and Account Manager are in the same Group that have layout in pattern | 1. Access Operator login screen 2. Login into seat follow pattern no 16 ( フリーシートユースケース sheet ) 3.On Seatmap Screen Logged in successfully by using Manager account ( View Mode ) | 3.1/ Seat login is refected follow pattern no 16 ( フリーシートユースケース sheet ) | ○ |  | Tien Tran
IT | IT-F-2-2-17 | 2 |  | 2 |  | 17 | Pattern No 17 | 1. Site Name, Layout, Location following pattern No 17 ( フリーシートユースケース sheet ) 2. OP and Account Manager are in the same Group that have layout in pattern | 1. Access Operator login screen 2. Login into seat follow pattern no 17 ( フリーシートユースケース sheet ) 3.On Seatmap Screen Logged in successfully by using Manager account ( View Mode ) | 3.1/ Seat login is refected follow pattern no 17 ( フリーシートユースケース sheet ) | ○ |  | Tien Tran
IT | IT-F-2-2-18 | 2 |  | 2 |  | 18 | Pattern No 18 | 1. Site Name, Layout, Location following pattern No 18 ( フリーシートユースケース sheet ) 2. OP and Account Manager are in the same Group that have layout in pattern | 1. Access Operator login screen 2. Login into seat follow pattern no 18 ( フリーシートユースケース sheet ) 3.On Seatmap Screen Logged in successfully by using Manager account ( View Mode ) | 3.1/ Seat login is refected follow pattern no 18 ( フリーシートユースケース sheet ) | ○ |  | Tien Tran
IT | IT-F-2-2-19 | 2 |  | 2 |  | 19 | Pattern No 19 | 1. Site Name, Layout, Location following pattern No 19 ( フリーシートユースケース sheet ) 2. OP and Account Manager are in the same Group that have layout in pattern | 1. Access Operator login screen 2. Login into seat follow pattern no 19 ( フリーシートユースケース sheet ) 3.On Seatmap Screen Logged in successfully by using Manager account ( View Mode ) | 3.1/ Seat login is refected follow pattern no 19 ( フリーシートユースケース sheet ) | ○ |  | Tien Tran
IT | IT-F-2-2-20 | 2 |  | 2 |  | 20 | Pattern No 20 | 1. Site Name, Layout, Location following pattern No 20 ( フリーシートユースケース sheet ) 2. OP and Account Manager are in the same Group that have layout in pattern | 1. Access Operator login screen 2. Login into seat follow pattern no 20 ( フリーシートユースケース sheet ) 3.On Seatmap Screen Logged in successfully by using Manager account ( View Mode ) | 3.1/ Seat login is refected follow pattern no 20 ( フリーシートユースケース sheet ) | ○ |  | Tien Tran
IT | IT-F-2-2-21 | 2 |  | 2 |  | 21 | Pattern No 21 | 1. Site Name, Layout, Location following pattern No 21 ( フリーシートユースケース sheet ) 2. OP and Account Manager are in the same Group that have layout in pattern | 1. Access Operator login screen 2. Login into seat follow pattern no 21 ( フリーシートユースケース sheet ) 3.On Seatmap Screen Logged in successfully by using Manager account ( View Mode ) | 3.1/ Seat login is refected follow pattern no 21 ( フリーシートユースケース sheet ) | ○ |  | Tien Tran
IT | IT-F-2-2-22 | 2 |  | 2 |  | 22 | Pattern No 22 | 1. Site Name, Layout, Location following pattern No 22 ( フリーシートユースケース sheet ) 2. OP and Account Manager are in the same Group that have layout in pattern | 1. Access Operator login screen 2. Login into seat follow pattern no 22 ( フリーシートユースケース sheet ) 3.On Seatmap Screen Logged in successfully by using Manager account ( View Mode ) | 3.1/ Seat login is refected follow pattern no 22 ( フリーシートユースケース sheet ) | ○ |  | Tien Tran
IT | IT-F-2-2-23 | 2 |  | 2 |  | 23 | Pattern No 23 | 1. Site Name, Layout, Location following pattern No 23 ( フリーシートユースケース sheet ) 2. OP and Account Manager are in the same Group that have layout in pattern | 1. Access Operator login screen 2. Login into seat follow pattern no 23 ( フリーシートユースケース sheet ) 3.On Seatmap Screen Logged in successfully by using Manager account ( View Mode ) | 3.1/ Seat login is refected follow pattern no 23 ( フリーシートユースケース sheet ) | ○ |  | Tien Tran
IT | IT-F-2-2-24 | 2 |  | 2 |  | 24 | Pattern No 24 | 1. Site Name, Layout, Location following pattern No 24 ( フリーシートユースケース sheet ) 2. OP and Account Manager are in the same Group that have layout in pattern | 1. Access Operator login screen 2. Login into seat follow pattern no 24 ( フリーシートユースケース sheet ) 3.On Seatmap Screen Logged in successfully by using Manager account ( View Mode ) | 3.1/ Seat login is refected follow pattern no 24 ( フリーシートユースケース sheet ) | ○ |  | Tien Tran
IT | IT-F-2-3-1 | 2 |  | 3 | Login via URL - Confirm query params | 1 | Success with correct param | 1. The following FreeSeat has been set on seatmap ・Site Name: FreeSeatSettingTest ・Layout: FreeSeat Layout ・Location: - FreeSeat1 - FreeSeat2 | 1. Access URL [/operator?site_name=xxx&layout_name=yyy&location_name=zzz] with below info ・xxxx: FreeSeatSettingTest ・yyyy: FreeSeat Layout ・zzzz: FreeSeat2 2.On GenesysCloud Login screen input info to login | 2.1. Logged in successfully 2.2. Communication Client is shown in new tab | ○ |  | Duc Huy
IT | IT-F-2-3-2 | 2 |  | 3 |  | 2 | Success without layout_name param ( single layout ) | 1. The following FreeSeat has been set on seatmap ・Site Name: FreeSeatSettingTest ・Layout: FreeSeat Layout ・Location: - FreeSeat1 - FreeSeat2 | 1. Access URL [/operator?site_name=xxx&location_name=zzz] with below info ・xxxx: FreeSeatSettingTest ・zzzz: FreeSeat2 2.On GenesysCloud Login screen input info to login | 2.1. Logged in successfully 2.2. Communication Client is shown in new tab | ○ |  | Duc Huy
IT | IT-F-2-3-3 | 2 |  | 3 |  | 3 | Success without layout_name param ( multi layout ) | 1. The following FreeSeat has been set on seatmap ・Site Name: FreeSeatSettingTest ・Layout: FreeSeat Layout ・Location: - FreeSeat1 - FreeSeat2 ・Site Name: FreeSeatSettingTest ・Layout: FreeSeat Layout2 ・Location: - FreeSeat1 | 1. Access URL [/operator?site_name=xxx&location_name=zzz] with below info ・xxxx: FreeSeatSettingTest ・zzzz: FreeSeat1 2.On GenesysCloud Login screen input info to login | 2.1. Logged in successfully 2.2. Communication Client is shown in new tab | ○ |  | Duc Huy
IT | IT-F-2-3-4 | 2 |  | 3 |  | 4 | Success with layout_name not have value ( single layout ) | 1. The following FreeSeat has been set on seatmap ・Site Name: FreeSeatSettingTest ・Layout: FreeSeat Layout ・Location: - FreeSeat1 - FreeSeat2 | 1. Access URL [/operator?site_name=xxx&layout_name=&location_name=zzz] with below info ・xxxx: FreeSeatSettingTest ・zzzz: FreeSeat2 2.On GenesysCloud Login screen input info to login | 2.1. Logged in successfully 2.2. Communication Client is shown in new tab | ○ |  | Duc Huy
IT | IT-F-2-3-5 | 2 |  | 3 |  | 5 | Success with layout_name not have value ( multi layout ) | 1. The following FreeSeat has been set on seatmap ・Site Name: FreeSeatSettingTest ・Layout: FreeSeat Layout ・Location: - FreeSeat1 - FreeSeat2 ・Site Name: FreeSeatSettingTest ・Layout: FreeSeat Layout2 ・Location: - FreeSeat1 | 1. Access URL [/operator?site_name=xxx&layout_name=&location_name=zzz] with below info ・xxxx: FreeSeatSettingTest ・zzzz: FreeSeat2 2.On GenesysCloud Login screen input info to login | 2.1. Logged in successfully 2.2. Communication Client is shown in new tab | ○ |  | Duc Huy
IT | IT-F-2-3-6 | 2 |  | 3 |  | 6 | Failed with location_name not exist in data | 1. The following FreeSeat has been set on seatmap ・Site Name: FreeSeatSettingTest ・Layout: FreeSeat Layout ・Location: - FreeSeat1 - FreeSeat2 | 1. Access URL [/operator?site_name=xxx&layout_name=yyy&location_name=zzz] with below info ・xxxx: FreeSeatSettingTest ・yyyy: FreeSeat Layout ・zzzz: FreeSeat3 | 2.1. Login is failed and message error is shown | ○ |  | Duc Huy
IT | IT-F-2-3-7 | 2 |  | 3 |  | 7 | Failed with site_name not exist in data | 1. The following FreeSeat has been set on seatmap ・Site Name: FreeSeatSettingTest ・Layout: FreeSeat Layout ・Location: - FreeSeat1 - FreeSeat2 | 1. Access URL [/operator?site_name=xxx&layout_name=yyy&location_name=zzz] with below info ・xxxx: FreeSeatSettingTest1 ・yyyy: FreeSeat Layout ・zzzz: FreeSeat2 | 2.1. Login is failed and message error is shown | ○ |  | Duc Huy
IT | IT-F-2-3-8 | 2 |  | 3 |  | 8 | Failed with without location_name param | 1. The following FreeSeat has been set on seatmap ・Site Name: FreeSeatSettingTest ・Layout: FreeSeat Layout ・Location: - FreeSeat1 - FreeSeat2 | 1. Access URL [/operator?site_name=xxx&layout_name=yyy] with below info ・xxxx: FreeSeatSettingTest ・yyyy: FreeSeat Layout | 2.1. Login is failed and message error is shown | ○ |  | Duc Huy
IT | IT-F-2-3-9 | 2 |  | 3 |  | 9 | Failed with without site_name param | 1. The following FreeSeat has been set on seatmap ・Site Name: FreeSeatSettingTest ・Layout: FreeSeat Layout ・Location: - FreeSeat1 - FreeSeat2 | 1. Access URL [/operator?layout_name=yyy&location_name=zzz] with below info ・yyyy: FreeSeat Layout ・zzzz: FreeSeat2 | 2.1. Login is failed and message error is shown | ○ |  | Duc Huy
IT | IT-F-2-4-2 | 2 |  | 4 | Login via URL - Supervisor account | 1 | Pattern No 1 | 1. Site Name, Layout, Location following pattern No 1 ( フリーシートユースケース sheet ) 2. OP and Account Supervisor are in the same Group that have layout in pattern | 1. Access Operator login screen 2. Login into seat follow pattern no 1 ( フリーシートユースケース sheet ) 3.On Seatmap Screen Logged in successfully by using Supervisor account | 3.1/ Seat login is refected follow pattern no 1 ( フリーシートユースケース sheet ) | ○ |  | Duc Huy
IT | IT-F-2-4-2 | 2 |  | 4 |  | 2 | Pattern No 2 | 1. Site Name, Layout, Location following pattern No 2 ( フリーシートユースケース sheet ) 2. OP and Account Supervisor are in the same Group that have layout in pattern | 1. Access Operator login screen 2. Login into seat follow pattern no 2 ( フリーシートユースケース sheet ) 3.On Seatmap Screen Logged in successfully by using Supervisor account | 3.1/ Seat login is refected follow pattern no 2 ( フリーシートユースケース sheet ) | ○ |  | Duc Huy
IT | IT-F-2-4-3 | 2 |  | 4 |  | 3 | Pattern No 3 | 1. Site Name, Layout, Location following pattern No 3 ( フリーシートユースケース sheet ) 2. OP and Account Supervisor are in the same Group that have layout in pattern | 1. Access Operator login screen 2. Login into seat follow pattern no 3 ( フリーシートユースケース sheet ) 3.On Seatmap Screen Logged in successfully by using Supervisor account | 3.1/ Seat login is refected follow pattern no 3 ( フリーシートユースケース sheet ) | ○ |  | Duc Huy
IT | IT-F-2-4-4 | 2 |  | 4 |  | 4 | Pattern No 4 | 1. Site Name, Layout, Location following pattern No 4 ( フリーシートユースケース sheet ) 2. OP and Account Supervisor are in the same Group that have layout in pattern | 1. Access Operator login screen 2. Login into seat follow pattern no 4 ( フリーシートユースケース sheet ) 3.On Seatmap Screen Logged in successfully by using Supervisor account | 3.1/ Seat login is refected follow pattern no 4 ( フリーシートユースケース sheet ) | ○ |  | Duc Huy
IT | IT-F-2-4-5 | 2 |  | 4 |  | 5 | Pattern No 5 | 1. Site Name, Layout, Location following pattern No 5 ( フリーシートユースケース sheet ) 2. OP and Account Supervisor are in the same Group that have layout in pattern | 1. Access Operator login screen 2. Login into seat follow pattern no 5 ( フリーシートユースケース sheet ) 3.On Seatmap Screen Logged in successfully by using Supervisor account | 3.1/ Seat login is refected follow pattern no 5 ( フリーシートユースケース sheet ) | ○ |  | Duc Huy
IT | IT-F-2-4-6 | 2 |  | 4 |  | 6 | Pattern No 6 | 1. Site Name, Layout, Location following pattern No 6 ( フリーシートユースケース sheet ) 2. OP and Account Supervisor are in the same Group that have layout in pattern | 1. Access Operator login screen 2. Login into seat follow pattern no 6( フリーシートユースケース sheet ) 3.On Seatmap Screen Logged in successfully by using Supervisor account | 3.1/ Seat login is refected follow pattern no 6 ( フリーシートユースケース sheet ) | ○ |  | Duc Huy
IT | IT-F-2-4-7 | 2 |  | 4 |  | 7 | Pattern No 7 | 1. Site Name, Layout, Location following pattern No 7 ( フリーシートユースケース sheet ) 2. OP and Account Supervisor are not in the same Group that have layout in pattern | 1. Access Operator login screen 2. Login into seat follow pattern no 7 ( フリーシートユースケース sheet ) 3.On Seatmap Screen Logged in successfully by using Supervisor account | 3.1/ Seat login is refected follow pattern no 7 ( フリーシートユースケース sheet ) | ○ |  | Duc Huy
IT | IT-F-2-4-8 | 2 |  | 4 |  | 8 | Pattern No 8 | 1. Site Name, Layout, Location following pattern No 8 ( フリーシートユースケース sheet ) 2. OP and Account Supervisor are not in the same Group that have layout in pattern | 1. Access Operator login screen 2. Login into seat follow pattern no 8 ( フリーシートユースケース sheet ) 3.On Seatmap Screen Logged in successfully by using Supervisor account | 3.1/ Seat login is refected follow pattern no 8 ( フリーシートユースケース sheet ) | ○ |  | Duc Huy
IT | IT-F-2-4-9 | 2 |  | 4 |  | 9 | Pattern No 9 | 1. Site Name, Layout, Location following pattern No 9 ( フリーシートユースケース sheet ) 2. OP and Account Supervisor are not in the same Group that have layout in pattern | 1. Access Operator login screen 2. Login into seat follow pattern no 9 ( フリーシートユースケース sheet ) 3.On Seatmap Screen Logged in successfully by using Supervisor account | 3.1/ Seat login is refected follow pattern no 9( フリーシートユースケース sheet ) | ○ |  | Duc Huy
IT | IT-F-2-4-10 | 2 |  | 4 |  | 10 | Pattern No 10 | 1. Site Name, Layout, Location following pattern No 10 ( フリーシートユースケース sheet ) 2. OP and Account Supervisor are not in the same Group that have layout in pattern | 1. Access Operator login screen 2. Login into seat follow pattern no 10 ( フリーシートユースケース sheet ) 3.On Seatmap Screen Logged in successfully by using Supervisor account | 3.1/ Seat login is refected follow pattern no 10 ( フリーシートユースケース sheet ) | ○ |  | Duc Huy
IT | IT-F-2-4-11 | 2 |  | 4 |  | 11 | Pattern No 11 | 1. Site Name, Layout, Location following pattern No 11 ( フリーシートユースケース sheet ) 2. OP and Account Supervisor are not in the same Group that have layout in pattern | 1. Access Operator login screen 2. Login into seat follow pattern no 11 ( フリーシートユースケース sheet ) 3.On Seatmap Screen Logged in successfully by using Supervisor account | 3.1/ Seat login is refected follow pattern no 11 ( フリーシートユースケース sheet ) | ○ |  | Duc Huy
IT | IT-F-2-4-12 | 2 |  | 4 |  | 12 | Pattern No 12 | 1. Site Name, Layout, Location following pattern No 12 ( フリーシートユースケース sheet ) 2. OP and Account Supervisor are not in the same Group that have layout in pattern | 1. Access Operator login screen 2. Login into seat follow pattern no 12 ( フリーシートユースケース sheet ) 3.On Seatmap Screen Logged in successfully by using Supervisor account | 3.1/ Seat login is refected follow pattern no 12 ( フリーシートユースケース sheet ) | ○ |  | Duc Huy
IT | IT-F-2-4-13 | 2 |  | 4 |  | 13 | Pattern No 13 | 1. Site Name, Layout, Location following pattern No 13 ( フリーシートユースケース sheet ) 2. OP and Account Supervisor in the same Group that have layout in pattern | 1. Access Operator login screen 2. Login into seat follow pattern no 13 ( フリーシートユースケース sheet ) 3.On Seatmap Screen Logged in successfully by using Supervisor account | 3.1/ Seat login is refected follow pattern no 13 ( フリーシートユースケース sheet ) | ○ |  | Duc Huy
IT | IT-F-2-4-14 | 2 |  | 4 |  | 14 | Pattern No 14 | 1. Site Name, Layout, Location following pattern No 14 ( フリーシートユースケース sheet ) 2. OP and Account Supervisor in the same Group that have layout in pattern | 1. Access Operator login screen 2. Login into seat follow pattern no 14 ( フリーシートユースケース sheet ) 3.On Seatmap Screen Logged in successfully by using Supervisor account | 3.1/ Seat login is refected follow pattern no 14 ( フリーシートユースケース sheet ) | ○ |  | Duc Huy
IT | IT-F-2-4-15 | 2 |  | 4 |  | 15 | Pattern No 15 | 1. Site Name, Layout, Location following pattern No 15 ( フリーシートユースケース sheet ) 2. OP and Account Supervisor in the same Group that have layout in pattern | 1. Access Operator login screen 2. Login into seat follow pattern no 15 ( フリーシートユースケース sheet ) 3.On Seatmap Screen Logged in successfully by using Supervisor account | 3.1/ Seat login is refected follow pattern no 15 ( フリーシートユースケース sheet ) | ○ |  | Duc Huy
IT | IT-F-2-4-16 | 2 |  | 4 |  | 16 | Pattern No 16 | 1. Site Name, Layout, Location following pattern No 16 ( フリーシートユースケース sheet ) 2. OP and Account Supervisor in the same Group that have layout in pattern | 1. Access Operator login screen 2. Login into seat follow pattern no 16 ( フリーシートユースケース sheet ) 3.On Seatmap Screen Logged in successfully by using Supervisor account | 3.1/ Seat login is refected follow pattern no 16 ( フリーシートユースケース sheet ) | ○ |  | Duc Huy
IT | IT-F-2-4-17 | 2 |  | 4 |  | 17 | Pattern No 17 | 1. Site Name, Layout, Location following pattern No 17 ( フリーシートユースケース sheet ) 2. OP and Account Supervisor in the same Group that have layout in pattern | 1. Access Operator login screen 2. Login into seat follow pattern no 17 ( フリーシートユースケース sheet ) 3.On Seatmap Screen Logged in successfully by using Supervisor account | 3.1/ Seat login is refected follow pattern no 17 ( フリーシートユースケース sheet ) | ○ |  | Duc Huy
IT | IT-F-2-4-18 | 2 |  | 4 |  | 18 | Pattern No 18 | 1. Site Name, Layout, Location following pattern No 18 ( フリーシートユースケース sheet ) 2. OP and Account Supervisor in the same Group that have layout in pattern | 1. Access Operator login screen 2. Login into seat follow pattern no 18 ( フリーシートユースケース sheet ) 3.On Seatmap Screen Logged in successfully by using Supervisor account | 3.1/ Seat login is refected follow pattern no 18 ( フリーシートユースケース sheet ) | ○ |  | Duc Huy
IT | IT-F-2-4-19 | 2 |  | 4 |  | 19 | Pattern No 19 | 1. Site Name, Layout, Location following pattern No 19 ( フリーシートユースケース sheet ) 2. OP and Account Supervisor are not in the same Group that have layout in pattern | 1. Access Operator login screen 2. Login into seat follow pattern no 19 ( フリーシートユースケース sheet ) 3.On Seatmap Screen Logged in successfully by using Supervisor account | 3.1/ Seat login is refected follow pattern no 19 ( フリーシートユースケース sheet ) | ○ |  | Duc Huy
IT | IT-F-2-4-20 | 2 |  | 4 |  | 20 | Pattern No 20 | 1. Site Name, Layout, Location following pattern No 20 ( フリーシートユースケース sheet ) 2. OP and Account Supervisor are not in the same Group that have layout in pattern | 1. Access Operator login screen 2. Login into seat follow pattern no 20 ( フリーシートユースケース sheet ) 3.On Seatmap Screen Logged in successfully by using Supervisor account | 3.1/ Seat login is refected follow pattern no 20 ( フリーシートユースケース sheet ) | ○ |  | Duc Huy
IT | IT-F-2-4-21 | 2 |  | 4 |  | 21 | Pattern No 21 | 1. Site Name, Layout, Location following pattern No 21 ( フリーシートユースケース sheet ) 2. OP and Account Supervisor are not in the same Group that have layout in pattern | 1. Access Operator login screen 2. Login into seat follow pattern no 21 ( フリーシートユースケース sheet ) 3.On Seatmap Screen Logged in successfully by using Supervisor account | 3.1/ Seat login is refected follow pattern no 21 ( フリーシートユースケース sheet ) | ○ |  | Duc Huy
IT | IT-F-2-4-22 | 2 |  | 4 |  | 22 | Pattern No 22 | 1. Site Name, Layout, Location following pattern No 22 ( フリーシートユースケース sheet ) 2. OP and Account Supervisor are not in the same Group that have layout in pattern | 1. Access Operator login screen 2. Login into seat follow pattern no 22 ( フリーシートユースケース sheet ) 3.On Seatmap Screen Logged in successfully by using Supervisor account | 3.1/ Seat login is refected follow pattern no 22 ( フリーシートユースケース sheet ) | ○ |  | Duc Huy
IT | IT-F-2-4-23 | 2 |  | 4 |  | 23 | Pattern No 23 | 1. Site Name, Layout, Location following pattern No 23 ( フリーシートユースケース sheet ) 2. OP and Account Supervisor are not in the same Group that have layout in pattern | 1. Access Operator login screen 2. Login into seat follow pattern no 23 ( フリーシートユースケース sheet ) 3.On Seatmap Screen Logged in successfully by using Supervisor account | 3.1/ Seat login is refected follow pattern no 23 ( フリーシートユースケース sheet ) | ○ |  | Duc Huy
IT | IT-F-2-4-24 | 2 |  | 4 |  | 24 | Pattern No 24 | 1. Site Name, Layout, Location following pattern No 24 ( フリーシートユースケース sheet ) 2. OP and Account Supervisor are not in the same Group that have layout in pattern | 1. Access Operator login screen 2. Login into seat follow pattern no 24 ( フリーシートユースケース sheet ) 3.On Seatmap Screen Logged in successfully by using Supervisor account | 3.1/ Seat login is refected follow pattern no 24 ( フリーシートユースケース sheet ) | ○ |  | Duc Huy
IT | IT-F-2-5-1 | 2 |  | 5 | Login via URL - Manager Account (View Mode) | 1 | Pattern No 1 | 1. Site Name, Layout, Location following pattern No 1 ( フリーシートユースケース sheet ) 2. OP and Account Manager are in the same Group that have layout in pattern | 1. Access Operator login screen 2. Login into seat follow pattern no 1 ( フリーシートユースケース sheet ) 3.On Seatmap Screen Logged in successfully by using Manager account ( View Mode ) | 3.1/ Seat login is refected follow pattern no 1 ( フリーシートユースケース sheet ) | ○ |  | Duc Huy
IT | IT-F-2-5-2 | 2 |  | 5 |  | 2 | Pattern No 2 | 1. Site Name, Layout, Location following pattern No 2 ( フリーシートユースケース sheet ) 2. OP and Account Manager are in the same Group that have layout in pattern | 1. Access Operator login screen 2. Login into seat follow pattern no 2 ( フリーシートユースケース sheet ) 3.On Seatmap Screen Logged in successfully by using Manager account ( View Mode ) | 3.1/ Seat login is refected follow pattern no 2 ( フリーシートユースケース sheet ) | ○ |  | Duc Huy
IT | IT-F-2-5-3 | 2 |  | 5 |  | 3 | Pattern No 3 | 1. Site Name, Layout, Location following pattern No 3 ( フリーシートユースケース sheet ) 2. OP and Account Manager are in the same Group that have layout in pattern | 1. Access Operator login screen 2. Login into seat follow pattern no 3 ( フリーシートユースケース sheet ) 3.On Seatmap Screen Logged in successfully by using Manager account ( View Mode ) | 3.1/ Seat login is refected follow pattern no 3 ( フリーシートユースケース sheet ) | ○ |  | Duc Huy
IT | IT-F-2-5-4 | 2 |  | 5 |  | 4 | Pattern No 4 | 1. Site Name, Layout, Location following pattern No 4 ( フリーシートユースケース sheet ) 2. OP and Account Manager are in the same Group that have layout in pattern | 1. Access Operator login screen 2. Login into seat follow pattern no 4 ( フリーシートユースケース sheet ) 3.On Seatmap Screen Logged in successfully by using Manager account ( View Mode ) | 3.1/ Seat login is refected follow pattern no 4 ( フリーシートユースケース sheet ) | ○ |  | Duc Huy
IT | IT-F-2-5-5 | 2 |  | 5 |  | 5 | Pattern No 5 | 1. Site Name, Layout, Location following pattern No 5 ( フリーシートユースケース sheet ) 2. OP and Account Manager are in the same Group that have layout in pattern | 1. Access Operator login screen 2. Login into seat follow pattern no 5 ( フリーシートユースケース sheet ) 3.On Seatmap Screen Logged in successfully by using Manager account ( View Mode ) | 3.1/ Seat login is refected follow pattern no 5 ( フリーシートユースケース sheet ) | ○ |  | Duc Huy
IT | IT-F-2-5-6 | 2 |  | 5 |  | 6 | Pattern No 6 | 1. Site Name, Layout, Location following pattern No 6 ( フリーシートユースケース sheet ) 2. OP and Account Manager are in the same Group that have layout in pattern | 1. Access Operator login screen 2. Login into seat follow pattern no 6 ( フリーシートユースケース sheet ) 3.On Seatmap Screen Logged in successfully by using Manager account ( View Mode ) | 3.1/ Seat login is refected follow pattern no 6 ( フリーシートユースケース sheet ) | ○ |  | Duc Huy
IT | IT-F-2-5-7 | 2 |  | 5 |  | 7 | Pattern No 7 | 1. Site Name, Layout, Location following pattern No 7 ( フリーシートユースケース sheet ) 2. OP and Account Manager are in the same Group that have layout in pattern | 1. Access Operator login screen 2. Login into seat follow pattern no 7 ( フリーシートユースケース sheet ) 3.On Seatmap Screen Logged in successfully by using Manager account ( View Mode ) | 3.1/ Seat login is refected follow pattern no 7 ( フリーシートユースケース sheet ) | ○ |  | Duc Huy
IT | IT-F-2-5-8 | 2 |  | 5 |  | 8 | Pattern No 8 | 1. Site Name, Layout, Location following pattern No 8 ( フリーシートユースケース sheet ) 2. OP and Account Manager are in the same Group that have layout in pattern | 1. Access Operator login screen 2. Login into seat follow pattern no 8 ( フリーシートユースケース sheet ) 3.On Seatmap Screen Logged in successfully by using Manager account ( View Mode ) | 3.1/ Seat login is refected follow pattern no 8 ( フリーシートユースケース sheet ) | ○ |  | Duc Huy
IT | IT-F-2-5-9 | 2 |  | 5 |  | 9 | Pattern No 9 | 1. Site Name, Layout, Location following pattern No 9 ( フリーシートユースケース sheet ) 2. OP and Account Manager are in the same Group that have layout in pattern | 1. Access Operator login screen 2. Login into seat follow pattern no 9 ( フリーシートユースケース sheet ) 3.On Seatmap Screen Logged in successfully by using Manager account ( View Mode ) | 3.1/ Seat login is refected follow pattern no 9( フリーシートユースケース sheet ) | ○ |  | Duc Huy
IT | IT-F-2-5-10 | 2 |  | 5 |  | 10 | Pattern No 10 | 1. Site Name, Layout, Location following pattern No 10 ( フリーシートユースケース sheet ) 2. OP and Account Manager are in the same Group that have layout in pattern | 1. Access Operator login screen 2. Login into seat follow pattern no 10 ( フリーシートユースケース sheet ) 3.On Seatmap Screen Logged in successfully by using Manager account ( View Mode ) | 3.1/ Seat login is refected follow pattern no 10 ( フリーシートユースケース sheet ) | ○ |  | Duc Huy
IT | IT-F-2-5-11 | 2 |  | 5 |  | 11 | Pattern No 11 | 1. Site Name, Layout, Location following pattern No 11 ( フリーシートユースケース sheet ) 2. OP and Account Manager are in the same Group that have layout in pattern | 1. Access Operator login screen 2. Login into seat follow pattern no 11 ( フリーシートユースケース sheet ) 3.On Seatmap Screen Logged in successfully by using Manager account ( View Mode ) | 3.1/ Seat login is refected follow pattern no 11 ( フリーシートユースケース sheet ) | ○ |  | Duc Huy
IT | IT-F-2-5-12 | 2 |  | 5 |  | 12 | Pattern No 12 | 1. Site Name, Layout, Location following pattern No 12 ( フリーシートユースケース sheet ) 2. OP and Account Manager are in the same Group that have layout in pattern | 1. Access Operator login screen 2. Login into seat follow pattern no 12 ( フリーシートユースケース sheet ) 3.On Seatmap Screen Logged in successfully by using Manager account ( View Mode ) | 3.1/ Seat login is refected follow pattern no 12 ( フリーシートユースケース sheet ) | ○ |  | Duc Huy
IT | IT-F-2-5-13 | 2 |  | 5 |  | 13 | Pattern No 13 | 1. Site Name, Layout, Location following pattern No 13 ( フリーシートユースケース sheet ) 2. OP and Account Manager are in the same Group that have layout in pattern | 1. Access Operator login screen 2. Login into seat follow pattern no 13 ( フリーシートユースケース sheet ) 3.On Seatmap Screen Logged in successfully by using Manager account ( View Mode ) | 3.1/ Seat login is refected follow pattern no 13 ( フリーシートユースケース sheet ) | ○ |  | Duc Huy
IT | IT-F-2-5-14 | 2 |  | 5 |  | 14 | Pattern No 14 | 1. Site Name, Layout, Location following pattern No 14 ( フリーシートユースケース sheet ) 2. OP and Account Manager are in the same Group that have layout in pattern | 1. Access Operator login screen 2. Login into seat follow pattern no 14 ( フリーシートユースケース sheet ) 3.On Seatmap Screen Logged in successfully by using Manager account ( View Mode ) | 3.1/ Seat login is refected follow pattern no 14 ( フリーシートユースケース sheet ) | ○ |  | Duc Huy
IT | IT-F-2-5-15 | 2 |  | 5 |  | 15 | Pattern No 15 | 1. Site Name, Layout, Location following pattern No 15 ( フリーシートユースケース sheet ) 2. OP and Account Manager are in the same Group that have layout in pattern | 1. Access Operator login screen 2. Login into seat follow pattern no 15 ( フリーシートユースケース sheet ) 3.On Seatmap Screen Logged in successfully by using Manager account ( View Mode ) | 3.1/ Seat login is refected follow pattern no 15 ( フリーシートユースケース sheet ) | ○ |  | Duc Huy
IT | IT-F-2-5-16 | 2 |  | 5 |  | 16 | Pattern No 16 | 1. Site Name, Layout, Location following pattern No 16 ( フリーシートユースケース sheet ) 2. OP and Account Manager are in the same Group that have layout in pattern | 1. Access Operator login screen 2. Login into seat follow pattern no 16 ( フリーシートユースケース sheet ) 3.On Seatmap Screen Logged in successfully by using Manager account ( View Mode ) | 3.1/ Seat login is refected follow pattern no 16 ( フリーシートユースケース sheet ) | ○ |  | Duc Huy
IT | IT-F-2-5-17 | 2 |  | 5 |  | 17 | Pattern No 17 | 1. Site Name, Layout, Location following pattern No 17 ( フリーシートユースケース sheet ) 2. OP and Account Manager are in the same Group that have layout in pattern | 1. Access Operator login screen 2. Login into seat follow pattern no 17 ( フリーシートユースケース sheet ) 3.On Seatmap Screen Logged in successfully by using Manager account ( View Mode ) | 3.1/ Seat login is refected follow pattern no 17 ( フリーシートユースケース sheet ) | ○ |  | Duc Huy
IT | IT-F-2-5-18 | 2 |  | 5 |  | 18 | Pattern No 18 | 1. Site Name, Layout, Location following pattern No 18 ( フリーシートユースケース sheet ) 2. OP and Account Manager are in the same Group that have layout in pattern | 1. Access Operator login screen 2. Login into seat follow pattern no 18 ( フリーシートユースケース sheet ) 3.On Seatmap Screen Logged in successfully by using Manager account ( View Mode ) | 3.1/ Seat login is refected follow pattern no 18 ( フリーシートユースケース sheet ) | ○ |  | Duc Huy
IT | IT-F-2-5-19 | 2 |  | 5 |  | 19 | Pattern No 19 | 1. Site Name, Layout, Location following pattern No 19 ( フリーシートユースケース sheet ) 2. OP and Account Manager are in the same Group that have layout in pattern | 1. Access Operator login screen 2. Login into seat follow pattern no 19 ( フリーシートユースケース sheet ) 3.On Seatmap Screen Logged in successfully by using Manager account ( View Mode ) | 3.1/ Seat login is refected follow pattern no 19 ( フリーシートユースケース sheet ) | ○ |  | Duc Huy
IT | IT-F-2-5-20 | 2 |  | 5 |  | 20 | Pattern No 20 | 1. Site Name, Layout, Location following pattern No 20 ( フリーシートユースケース sheet ) 2. OP and Account Manager are in the same Group that have layout in pattern | 1. Access Operator login screen 2. Login into seat follow pattern no 20 ( フリーシートユースケース sheet ) 3.On Seatmap Screen Logged in successfully by using Manager account ( View Mode ) | 3.1/ Seat login is refected follow pattern no 20 ( フリーシートユースケース sheet ) | ○ |  | Duc Huy
IT | IT-F-2-5-21 | 2 |  | 5 |  | 21 | Pattern No 21 | 1. Site Name, Layout, Location following pattern No 21 ( フリーシートユースケース sheet ) 2. OP and Account Manager are in the same Group that have layout in pattern | 1. Access Operator login screen 2. Login into seat follow pattern no 21 ( フリーシートユースケース sheet ) 3.On Seatmap Screen Logged in successfully by using Manager account ( View Mode ) | 3.1/ Seat login is refected follow pattern no 21 ( フリーシートユースケース sheet ) | ○ |  | Duc Huy
IT | IT-F-2-5-22 | 2 |  | 5 |  | 22 | Pattern No 22 | 1. Site Name, Layout, Location following pattern No 22 ( フリーシートユースケース sheet ) 2. OP and Account Manager are in the same Group that have layout in pattern | 1. Access Operator login screen 2. Login into seat follow pattern no 22 ( フリーシートユースケース sheet ) 3.On Seatmap Screen Logged in successfully by using Manager account ( View Mode ) | 3.1/ Seat login is refected follow pattern no 22 ( フリーシートユースケース sheet ) | ○ |  | Duc Huy
IT | IT-F-2-5-23 | 2 |  | 5 |  | 23 | Pattern No 23 | 1. Site Name, Layout, Location following pattern No 23 ( フリーシートユースケース sheet ) 2. OP and Account Manager are in the same Group that have layout in pattern | 1. Access Operator login screen 2. Login into seat follow pattern no 23 ( フリーシートユースケース sheet ) 3.On Seatmap Screen Logged in successfully by using Manager account ( View Mode ) | 3.1/ Seat login is refected follow pattern no 23 ( フリーシートユースケース sheet ) | ○ |  | Duc Huy
IT | IT-F-2-5-24 | 2 |  | 5 |  | 24 | Pattern No 24 | 1. Site Name, Layout, Location following pattern No 24 ( フリーシートユースケース sheet ) 2. OP and Account Manager are in the same Group that have layout in pattern | 1. Access Operator login screen 2. Login into seat follow pattern no 24 ( フリーシートユースケース sheet ) 3.On Seatmap Screen Logged in successfully by using Manager account ( View Mode ) | 3.1/ Seat login is refected follow pattern no 24 ( フリーシートユースケース sheet ) | ○ |  | Duc Huy

## Seatmap Screen
[12 empty] | Number of test items | 110 | OK | 52
[12 empty] | Not implemented | 58 | NG | 0
[12 empty] | Progress rate | 47.27% | NT | 0
工程 | ＮＯ | Test items | [5 empty] | Preconditions | Steps | Expected Results | 試験実施 有無 | Browser type | Test member | Test day | Test results | Questionnaire number | Retest member | Retest date | Retest result | Finished Day | Remarks
|  | Main category |  | Sub-category |  | Test Title
IT | IT-SS-1-1-1 | 1 | Setting freeseat | 1 | Display | 1 | List freeseat - Supervisor account | 1. The following FreeSeat has been set on seatmap ・Site Name: FreeSeatSettingTest ・Layout: FreeSeat Layout ・Location: - FreeSeat1 - FreeSeat2 | 1. Logged in seatmap successfully by using supervisor account 2. Select layout [FreeSeatSettingTest > FreeSeat Layout] | 2.1. The following Seats are shown on layout: - FreeSeat1 - FreeSeat2 | ○ |  | Hoang Nguyen
IT | IT-SS-1-1-2 | 1 |  | 1 |  | 2 | List freeseat - Manager account (View Mode) | 1. The following FreeSeat has been set on seatmap ・Site Name: FreeSeatSettingTest ・Layout: FreeSeat Layout ・Location: - FreeSeat1 - FreeSeat2 | 1. Logged in seatmap successfully by using manager account 2. Switch to view mode 3. Select layout [FreeSeatSettingTest > FreeSeat Layout] | 3.1. The following Seats are shown on layout: - FreeSeat1 - FreeSeat2 | ○ |  | Hoang Nguyen
IT | IT-SS-2-1-1 | 2 | Setting Layout | 1 | Add layout button | 1 | Add layout button display | 1. The following Layout has been set on seatmap ・Site Name: FreeSeatSettingTest ・Layout list: have < 30 layouts | 1. Logged in seatmap successfully by using admin account 2. Select Site Name [FreeSeatSettingTest] | 2.1/ Add layout button is display | ○ |  | Hoang Nguyen
IT | IT-SS-2-1-2 | 2 |  | 1 |  | 2 | Add layout button hidden | 1. The following Layout has been set on seatmap ・Site Name: FreeSeatSettingTest ・Layout list: have 30 layouts | 1. Logged in seatmap successfully by using admin account 2. Select Site Name [FreeSeatSettingTest] | 2.1/ Add layout button is hidden | ○ |  | Hoang Nguyen
IT | IT-SS-2-2-1 | 2 |  | 2 | Layout name | 1 | Add layout with layout name follow: - All layouts | 1. The following Layout has been set on seatmap ・Site Name: FreeSeatSettingTest | 1. Logged in seatmap successfully by using admin account 2. Select Site Name [FreeSeatSettingTest] 3. Add layout with name follow: - All layouts | 3.1/ Add layout failed | ○ |  | Hoang Nguyen
IT | IT-SS-2-2-2 | 2 |  | 2 |  | 2 | Add layout with layout name follow: - 全レイアウト | 1. The following Layout has been set on seatmap ・Site Name: FreeSeatSettingTest | 1. Logged in seatmap successfully by using admin account 2. Select Site Name [FreeSeatSettingTest] 3. Add layout with name follow: - 全レイアウト | 3.1/ Add layout failed | ○ |  | Hoang Nguyen
IT | IT-SS-3-1-1 | 3 | Freeseat logout state | 1 | Display | 1 | Confirm background color of layout is shown correctly - Supervisor account | 1. The following FreeSeat has been set on seatmap ・Site Name: FreeSeatSettingTest ・Layout: FreeSeat Layout ・Location: - FreeSeat1 - FreeSeat2 2. Logged in successfully by using Supervisor account 3. OP is not logged in | 1. View FreeSeat Layout | 1.1. Background of layout is gray | ○ |  | Hoang Nguyen
IT | IT-SS-3-1-2 | 3 |  | 1 |  | 2 | Confirm background color of layout is shown correctly - Manager account (View Mode) | 1. The following FreeSeat has been set on seatmap ・Site Name: FreeSeatSettingTest ・Layout: FreeSeat Layout ・Location: - FreeSeat1 - FreeSeat2 2. Logged in successfully by using Manager account 3. Switch to view mode 4. OP is not logged in | 1. View FreeSeat Layout | 1.1. Background of layout is gray | ○ |  | Hoang Nguyen
IT | IT-SS-3-1-3 | 3 |  | 1 |  | 3 | Confirm text of all control of layout is shown correctly - Supervisor account | 1. The following FreeSeat has been set on seatmap ・Site Name: FreeSeatSettingTest ・Layout: FreeSeat Layout ・Location: - FreeSeat1 - FreeSeat2 2. Logged in successfully by using supervisor account 3. OP is not logged in | 1. View FreeSeat Layout | 1.1. Control's text is shown as below: - Seat number: Seat Name - User name: - Status: - Time: | ○ |  | Hoang Nguyen
IT | IT-SS-3-1-4 | 3 |  | 1 |  | 4 | Confirm text of all control of layout is shown correctly - Manager account (View Mode) | 1. The following FreeSeat has been set on seatmap ・Site Name: FreeSeatSettingTest ・Layout: FreeSeat Layout ・Location: - FreeSeat1 - FreeSeat2 2. Logged in successfully by using Manager account 3. Switch to view mode 4. OP is not logged in | 1. View FreeSeat Layout | 1.1. Control's text is shown as below: - Seat number: Seat Name - User name: - Status: - Time: | ○ |  | Hoang Nguyen
IT | IT-SS-3-1-5 | 3 |  | 1 |  | 5 | Confirm menu popup on layout is disable - Supervisor account | 1. The following FreeSeat has been set on seatmap ・Site Name: FreeSeatSettingTest ・Layout: FreeSeat Layout ・Location: - FreeSeat1 - FreeSeat2 2. Logged in successfully by using supervisor account 3. OP is not logged in | 1. Right click on seat layout | 1.1/ Menu popup on layout by right click is disabled | ○ |  | Hoang Nguyen
IT | IT-SS-3-1-6 | 3 |  | 1 |  | 6 | Confirm menu popup on layout is disable - Manager account (View Mode) | 1. The following FreeSeat has been set on seatmap ・Site Name: FreeSeatSettingTest ・Layout: FreeSeat Layout ・Location: - FreeSeat1 - FreeSeat2 2. Logged in successfully by using Manager account 3. Switch to view mode 4. OP is not logged in | 1. Right click on seat layout | 1.1/ Menu popup on layout by right click is disabled | ○ |  | Hoang Nguyen
IT | IT-SS-3-2-1 | 3 |  | 2 | Freeseat login | 1 | Confirm background color of layout is shown correctly when freeseat login by - Supervisor account | 1. The following FreeSeat has been set on seatmap ・Site Name: FreeSeatSettingTest ・Layout: FreeSeat Layout ・FreeSeat: - FreeSeat1 - FreeSeat2 2. Create Group [ToTest] 3. Setting Supervisor and OP as below Manager/SV: supervisor account OP: 野澤 直紀 4. Mapping FreeSeat Layout with group [ToTest] 5. Logged in Map successfully by using supervisor account | 1. On Operator Client login screen select [FreeSeatSettingTest > FreeSeat Layout > FreeSeat1] and logged in successfully by 野澤 直紀 account 2. View Freeseat Layout | 2.1. Background of layout is green | ○ |  | Hoang Nguyen
IT | IT-SS-3-2-2 | 3 |  | 2 |  | 2 | Confirm background color of layout is shown correctly when freeseat login - Manager account (View Mode) | 1. The following FreeSeat has been set on seatmap ・Site Name: FreeSeatSettingTest ・Layout: FreeSeat Layout ・FreeSeat: - FreeSeat1 - FreeSeat2 2. Create Group [ToTest] 3. Setting Manager/ SV and OP as below Manager/SV: manager OP: 野澤 直紀 4. Mapping FreeSeat Layout with group [ToTest] 5. Logged in Map successfully by using manager account 6. Switch to view mode | 1. On Operator Client login screen select [FreeSeatSettingTest > FreeSeat Layout > FreeSeat1] and logged in successfully by 野澤 直紀 account 2. View Freeseat Layout | 2.1. Background of layout is green | ○ |  | Hoang Nguyen
IT | IT-SS-3-2-3 | 3 |  | 2 |  | 3 | Confirm text of all control of layout is shown correctly when freeseat login - Supervisor account | 1. The following FreeSeat has been set on seatmap ・Site Name: FreeSeatSettingTest ・Layout: FreeSeat Layout ・FreeSeat: - FreeSeat1 - FreeSeat2 2. Create Group [ToTest] 3. Setting Supervisor and OP as below Manager/SV: supervisor account OP: 野澤 直紀 4. Mapping FreeSeat Layout with group [ToTest] 5. Logged in Map successfully by using supervisor account | 1. On Operator Client login screen select [FreeSeatSettingTest > FreeSeat Layout > FreeSeat1] and logged in successfully by 野澤 直紀 account 2. View Freeseat Layout | 2.1. Control's text is shown as below: - Seat number: SeatNumber - User name: OP name - Status: OP Status - Time: total time from logged in timing (format: hh:mm:ss) | ○ |  | Hoang Nguyen
IT | IT-SS-3-2-4 | 3 |  | 2 |  | 4 | Confirm text of all control of layout is shown correctly when freeseat login - Manager account (View Mode) | 1. The following FreeSeat has been set on seatmap ・Site Name: FreeSeatSettingTest ・Layout: FreeSeat Layout ・FreeSeat: - FreeSeat1 - FreeSeat2 2. Create Group [ToTest] 3. Setting Manager/ SV and OP as below Manager/SV: manager OP: 野澤 直紀 4. Mapping FreeSeat Layout with group [ToTest] 5. Logged in Map successfully by using manager account 6. Switch to view mode | 1. On Operator Client login screen select [FreeSeatSettingTest > FreeSeat Layout > FreeSeat1] and logged in successfully by 野澤 直紀 account 2. View Freeseat Layout | 2.1. Control's text is shown as below: - Seat number: SeatNumber - User name: OP name - Status: OP Status - Time: total time from logged in timing (format: hh:mm:ss) | ○ |  | Hoang Nguyen
IT | IT-SS-3-2-5 | 3 |  | 2 |  | 5 | Confirm menu popup on layout enable - Supervisor account | 1. The following FreeSeat has been set on seatmap ・Site Name: FreeSeatSettingTest ・Layout: FreeSeat Layout ・FreeSeat: - FreeSeat1 - FreeSeat2 2. Create Group [ToTest] 3. Setting Supervisor and OP as below Manager/SV: supervisor account OP: 野澤 直紀 4. Mapping FreeSeat Layout with group [ToTest] 5. Logged in Map successfully by using supervisor account | 1. On Operator Client login screen select [FreeSeatSettingTest > FreeSeat Layout > FreeSeat1] and logged in successfully by 野澤 直紀 account 2. View Freeseat Layout | 2.1. Menu popup is displayed when right click on freeseat | ○ |  | Hoang Nguyen
IT | IT-SS-3-2-6 | 3 |  | 2 |  | 6 | Confirm menu popup on layout enable - Manager account (View Mode) | 1. The following FreeSeat has been set on seatmap ・Site Name: FreeSeatSettingTest ・Layout: FreeSeat Layout ・FreeSeat: - FreeSeat1 - FreeSeat2 2. Create Group [ToTest] 3. Setting Manager/ SV and OP as below Manager/SV: manager OP: 野澤 直紀 4. Mapping FreeSeat Layout with group [ToTest] 5. Logged in Map successfully by using manager account 6. Switch to view mode | 1. On Operator Client login screen select [FreeSeatSettingTest > FreeSeat Layout > FreeSeat1] and logged in successfully by 野澤 直紀 account 2. View Freeseat Layout | 2.1. Menu popup is displayed when right click on freeseat | ○ |  | Hoang Nguyen
IT | IT-SS-3-2-7 | 3 |  | 2 |  | 7 | Confirm multilayout is show correct - Supervisor account | 1. The following FreeSeat has been set on seatmap ・Site Name: FreeSeatSettingTest ・Layout: FreeSeat Layout ・FreeSeat: - FreeSeat1 - FreeSeat2 ・Site Name: FreeSeatSettingTest ・Layout: FreeSeat Layout2 ・FreeSeat: - FreeSeat1 2. Create Group [ToTest] 3. Setting Manager/ SV and OP as below Manager/SV: supervisor account OP: 野澤 直紀 4. Mapping FreeSeat Layout and FreeSeat Layout2 with group [ToTest] 5. Logged in Map successfully by using supervisor account | 1. On Operator Client login screen select [FreeSeatSettingTest > All layouts > FreeSeat1] and logged in successfully by 野澤 直紀 account 2. View Freeseat Layout | 2.1/ FreeSeat1 in FreeSeat Layout and FreeSeat Layout2 are reflected - Background is green - Control's Text: + Seat number: SeatNumber + User name: OP name + Status: OP Status + Time: total time from logged in timing (format: hh:mm:ss) - Menu popup is displayed when right click on freeseat | ○ |  | Hoang Nguyen
IT | IT-SS-3-2-8 | 3 |  | 2 |  | 8 | Confirm multilayout is show correct - Manager account (View Mode) | 1. The following FreeSeat has been set on seatmap ・Site Name: FreeSeatSettingTest ・Layout: FreeSeat Layout ・FreeSeat: - FreeSeat1 - FreeSeat2 ・Site Name: FreeSeatSettingTest ・Layout: FreeSeat Layout2 ・FreeSeat: - FreeSeat1 2. Create Group [ToTest] 3. Setting Manager/ SV and OP as below Manager/SV: manager OP: 野澤 直紀 4. Mapping FreeSeat Layout and FreeSeat Layout2 with group [ToTest] 5. Logged in Map successfully by using manager account 6. Switch to view mode | 1. On Operator Client login screen select [FreeSeatSettingTest > All layouts > FreeSeat1] and logged in successfully by 野澤 直紀 account 2. View Freeseat Layout | 2.1/ FreeSeat1 in FreeSeat Layout and FreeSeat Layout2 are reflected - Background is green - Control's Text: + Seat number: SeatNumber + User name: OP name + Status: OP Status + Time: total time from logged in timing (format: hh:mm:ss) - Menu popup is displayed when right click on freeseat | ○ |  | Hoang Nguyen
IT | IT-SS-4-1-1 | 4 | Freeseat logged in state | 1 | Display | 1 | Confirm background color of layout is shown correctly - Supervisor account | 1. The following FreeSeat has been set on seatmap ・Site Name: FreeSeatSettingTest ・Layout: FreeSeat Layout ・FreeSeat: - FreeSeat1 - FreeSeat2 2. Create Group [ToTest] 3. Setting Manager/ SV and OP as below Manager/SV: supervisor account OP: 野澤 直紀 4. Mapping FreeSeat Layout with group [ToTest] 5. Logged in Map successfully by using supervisor account 6. On Operator Client login screen select [FreeSeatSettingTest > FreeSeat Layout > FreeSeat2] and logged in successfully by 野澤 直紀 account | 1. View FreeSeat Layout | 1.1. Background of layout is green | ○ |  | Hoang Nguyen
IT | IT-SS-4-1-2 | 4 |  | 1 |  | 2 | Confirm background color of layout is shown correctly - Manager account (View Mode) | 1. The following FreeSeat has been set on seatmap ・Site Name: FreeSeatSettingTest ・Layout: FreeSeat Layout ・FreeSeat: - FreeSeat1 - FreeSeat2 2. Create Group [ToTest] 3. Setting Manager/ SV and OP as below Manager/SV: manager OP: 野澤 直紀 4. Mapping FreeSeat Layout with group [ToTest] 5. Logged in Map successfully by using manager account 6. Switch to view mode 7. On Operator Client login screen select [FreeSeatSettingTest > FreeSeat Layout > FreeSeat2] and logged in successfully by 野澤 直紀 account | 1. View FreeSeat Layout | 1.1. Background of layout is green | ○ |  | Hoang Nguyen
IT | IT-SS-4-1-3 | 4 |  | 1 |  | 3 | Confirm text of all control of layout is shown correctly - Supervisor account | 1. The following FreeSeat has been set on seatmap ・Site Name: FreeSeatSettingTest ・Layout: FreeSeat Layout ・FreeSeat: - FreeSeat1 - FreeSeat2 2. Create Group [ToTest] 3. Setting Manager/ SV and OP as below Manager/SV: supervisor account OP: 野澤 直紀 4. Mapping FreeSeat Layout with group [ToTest] 5. Logged in Map successfully by using supervisor account 6. On Operator Client login screen select [FreeSeatSettingTest > FreeSeat Layout > FreeSeat2] and logged in successfully by 野澤 直紀 account | 1. View FreeSeat Layout | 1.1.Control's text is shown as below: - Seat number: SeatName - User name: 野澤 直紀 - Status: OP Status - Time: total time from logged in timing (format: hh:mm:ss) | ○ |  | Hoang Nguyen
IT | IT-SS-4-1-4 | 4 |  | 1 |  | 4 | Confirm text of all control of layout is shown correctly - Manager account (View Mode) | 1. The following FreeSeat has been set on seatmap ・Site Name: FreeSeatSettingTest ・Layout: FreeSeat Layout ・FreeSeat: - FreeSeat1 - FreeSeat2 2. Create Group [ToTest] 3. Setting Manager/ SV and OP as below Manager/SV: manager OP: 野澤 直紀 4. Mapping FreeSeat Layout with group [ToTest] 5. Logged in Map successfully by using manager account 6. Switch to view mode 7. On Operator Client login screen select [FreeSeatSettingTest > FreeSeat Layout > FreeSeat2] and logged in successfully by 野澤 直紀 account | 1. View FreeSeat Layout | 1.1.Control's text is shown as below: - Seat number: SeatName - User name: 野澤 直紀 - Status: OP Status - Time: total time from logged in timing (format: hh:mm:ss) | ○ |  | Hoang Nguyen
IT | IT-SS-4-1-5 | 4 |  | 1 |  | 5 | Confirm menu popup on layout enable - Supervisor account | 1. The following FreeSeat has been set on seatmap ・Site Name: FreeSeatSettingTest ・Layout: FreeSeat Layout ・FreeSeat: - FreeSeat1 - FreeSeat2 2. Create Group [ToTest] 3. Setting Manager/ SV and OP as below Manager/SV: supervisor account OP: 野澤 直紀 4. Mapping FreeSeat Layout with group [ToTest] 5. Logged in Map successfully by using supervisor account 6. On Operator Client login screen select [FreeSeatSettingTest > FreeSeat Layout > FreeSeat2] and logged in successfully by 野澤 直紀 account | 1. Right click on seat layout | 1.1/ Menu popup on layout by right click is shown | ○ |  | Hoang Nguyen
IT | IT-SS-4-1-6 | 4 |  | 1 |  | 6 | Confirm menu popup on layout enable - Manager account (View Mode) | 1. The following FreeSeat has been set on seatmap ・Site Name: FreeSeatSettingTest ・Layout: FreeSeat Layout ・FreeSeat: - FreeSeat1 - FreeSeat2 2. Create Group [ToTest] 3. Setting Manager/ SV and OP as below Manager/SV: manager OP: 野澤 直紀 4. Mapping FreeSeat Layout with group [ToTest] 5. Logged in Map successfully by using manager account 6. Switch to view mode 7. On Operator Client login screen select [FreeSeatSettingTest > FreeSeat Layout > FreeSeat2] and logged in successfully by 野澤 直紀 account | 1. Right click on seat layout | 1.1/ Menu popup on layout by right click is shown | ○ |  | Hoang Nguyen
IT | IT-SS-4-1-7 | 4 |  | 1 |  | 7 | Confirm multilayout is show correct - Supervisor account | 1. The following FreeSeat has been set on seatmap ・Site Name: FreeSeatSettingTest ・Layout: FreeSeat Layout ・FreeSeat: - FreeSeat1 - FreeSeat2 ・Site Name: FreeSeatSettingTest ・Layout: FreeSeat Layout2 ・FreeSeat: - FreeSeat1 2. Create Group [ToTest] 3. Setting Manager/ SV and OP as below Manager/SV: supervisor account OP: 野澤 直紀 4. Mapping FreeSeat Layout and FreeSeat Layout2 with group [ToTest] 5. Logged in Map successfully by using manager account 6. On Operator Client login screen select [FreeSeatSettingTest > All layouts > FreeSeat1] and logged in successfully by 野澤 直紀 account | 1. View FreeSeat Layout | 1.1/ FreeSeat1 in FreeSeat Layout and FreeSeat Layout2 are reflected - Background is green - Control's Text: + Seat number: SeatNumber + User name: OP name + Status: OP Status + Time: total time from logged in timing (format: hh:mm:ss) - Menu popup is displayed when right click on freeseat | ○ |  | Hoang Nguyen
IT | IT-SS-4-1-8 | 4 |  | 1 |  | 8 | Confirm multilayout is show correct - Manager account (View Mode) | 1. The following FreeSeat has been set on seatmap ・Site Name: FreeSeatSettingTest ・Layout: FreeSeat Layout ・FreeSeat: - FreeSeat1 - FreeSeat2 ・Site Name: FreeSeatSettingTest ・Layout: FreeSeat Layout2 ・FreeSeat: - FreeSeat1 2. Create Group [ToTest] 3. Setting Manager/ SV and OP as below Manager/SV: manager OP: 野澤 直紀 4. Mapping FreeSeat Layout and FreeSeat Layout2 with group [ToTest] 5. Logged in Map successfully by using manager account 6. Switch to view mode 7. On Operator Client login screen select [FreeSeatSettingTest > All layouts > FreeSeat1] and logged in successfully by 野澤 直紀 account | 1. View FreeSeat Layout | 1.1/ FreeSeat1 in FreeSeat Layout and FreeSeat Layout2 are reflected - Background is green - Control's Text: + Seat number: SeatNumber + User name: OP name + Status: OP Status + Time: total time from logged in timing (format: hh:mm:ss) - Menu popup is displayed when right click on freeseat | ○ |  | Hoang Nguyen
IT | IT-SS-4-2-1 | 4 |  | 2 | Inbound Call Status Reflect - Manager account (View Mode) | 1 | On-Queue | 1. The following FreeSeat has been set on seatmap ・Site Name: FreeSeatSettingTest ・Layout: FreeSeatLayout ・FreeSeat: - FreeSeat1 - FreeSeat2 2. Create Group [ToTest] 3. Setting Manager/ SV and OP as below Manager/SV: manager OP: 野澤 直紀 4. Mapping FreeSeat Layout and FreeSeat Layout2 with group [ToTest] 5. Logged in Map successfully by using manager account 6. Switch to view mode 7. On Operator Client login screen select [FreeSeatSettingTest > FreeSeat1 FreeSeatLayout > FreeSeat1] and logged in successfully by 野澤 直紀 account | 1. On GC, set status to On Queue 2. View FreeSeat Layout | 2.1.Control's text is shown as below: - Seat number: SeatName - User name: 野澤 直紀 - Status: キュー中 - Time: total time from logged in timing (format: hh:mm:ss) 2.2 Background is light green | ○ |  | Cuong Bui | 2024-04-12 | OK
IT | IT-SS-4-2-2 | 4 |  | 2 |  | 2 | Alerting | 1. Continue with IT-SS-4-2-1 | 1. On GC receive an incoming external call 2. View FreeSeat Layout | 2.1.Control's text is shown as below: - Seat number: SeatName - User name: 野澤 直紀 - Status: アラーティング - Time: total time from logged in timing (format: hh:mm:ss) 2.2 Background is red | ○ |  | Cuong Bui | 2024-04-12 | OK
IT | IT-SS-4-2-3 | 4 |  | 2 |  | 3 | Answer incoming external call | 1. Continue with IT-SS-4-2-2 | 1. On GC answer an incoming external call 2. View FreeSeat Layout | 2.1.Control's text is shown as below: - Seat number: SeatName - User name: 野澤 直紀 - Status: 着信通話 - Time: total time from logged in timing (format: hh:mm:ss) 2.2 Background is red | ○ |  | Cuong Bui | 2024-04-12 | OK
IT | IT-SS-4-2-4 | 4 |  | 2 |  | 4 | On-Hold | 1. Continue with IT-SS-4-2-3 | 1. On GC click「保留」 button 2. View FreeSeat Layout | 2.1.Control's text is shown as below: - Seat number: SeatName - User name: 野澤 直紀 - Status: 保留 - Time: total time from logged in timing (format: hh:mm:ss) 2.2 Background is yellow | ○ |  | Cuong Bui | 2024-04-12 | OK
IT | IT-SS-4-2-5 | 4 |  | 2 |  | 5 | Release from hold | 1. Continue with IT-SS-4-4 | 1. On GC click「保留解除」 button 2. View FreeSeat Layout | 2.1.Control's text is shown as below: - Seat number: SeatName - User name: 野澤 直紀 - Status: 着信通話 - Time: total time from logged in timing (format: hh:mm:ss) 2.2 Background is red | ○ |  | Cuong Bui | 2024-04-12 | OK
IT | IT-SS-4-2-6 | 4 |  | 2 |  | 6 | Disconnect incoming external call | 1. Continue with IT-SS-4-2-5 | 1. On GC click「電話を切る」 button 2. View FreeSeat Layout | 2.1.Control's text is shown as below: - Seat number: SeatName - User name: 野澤 直紀 - Status: アフターワーク中 - Time: total time from logged in timing (format: hh:mm:ss) 2.2 Background is light blue | ○ |  | Cuong Bui | 2024-04-12 | OK
IT | IT-SS-4-2-7 | 4 |  | 2 |  | 7 | ACW Done | 1. Continue with IT-SS-4-2-6 | 1. On GC click「Done」 button 2. View FreeSeat Layout | 2.1.Control's text is shown as below: - Seat number: SeatName - User name: 野澤 直紀 - Status: キュー中 - Time: total time from logged in timing (format: hh:mm:ss) 2.2 Background is light green | ○ |  | Cuong Bui | 2024-04-12 | OK
IT | IT-SS-4-3-1 | 4 |  | 3 | Inbound Call Status Reflect - Supervisor account | 1 | On-Queue | 1. The following FreeSeat has been set on seatmap ・Site Name: FreeSeatSettingTest ・Layout: FreeSeat Layout ・FreeSeat: - FreeSeat1 - FreeSeat2 2. Create Group [ToTest] 3. Setting Manager/ SV and OP as below Manager/SV: supervisor account OP: 野澤 直紀 4. Mapping FreeSeat Layout and FreeSeat Layout2 with group [ToTest] 5. Logged in Map successfully by using supervisor account 7. On Operator Client login screen select [FreeSeatSettingTest > FreeSeat1 FreeSeatLayout > FreeSeat1] and logged in successfully by 野澤 直紀 account | 1. On GC, set status to On Queue 2. View FreeSeat Layout | 2.1.Control's text is shown as below: - Seat number: SeatName - User name: 野澤 直紀 - Status: キュー中 - Time: total time from logged in timing (format: hh:mm:ss) 2.2 Background is light green | ○ |  | Cuong Bui | 2024-04-12 | OK
IT | IT-SS-4-3-2 | 4 |  | 3 |  | 2 | Alerting | 1. Continue with IT-SS-4-3-1 | 1. On GC receive an incoming external call 2. View FreeSeat Layout | 2.1.Control's text is shown as below: - Seat number: SeatName - User name: 野澤 直紀 - Status: アラーティング - Time: total time from logged in timing (format: hh:mm:ss) 2.2 Background is red | ○ |  | Cuong Bui | 2024-04-12 | OK
IT | IT-SS-4-3-3 | 4 |  | 3 |  | 3 | Answer incoming external call | 1. Continue with IT-SS-4-3-2 | 1. On GC answer an incoming external call 2. View FreeSeat Layout | 2.1.Control's text is shown as below: - Seat number: SeatName - User name: 野澤 直紀 - Status: 着信通話 - Time: total time from logged in timing (format: hh:mm:ss) 2.2 Background is red | ○ |  | Cuong Bui | 2024-04-12 | OK
IT | IT-SS-4-3-4 | 4 |  | 3 |  | 4 | On-Hold | 1. Continue with IT-SS-4-3-3 | 1. On GC click「保留」 button 2. View FreeSeat Layout | 2.1.Control's text is shown as below: - Seat number: SeatName - User name: 野澤 直紀 - Status: 保留 - Time: total time from logged in timing (format: hh:mm:ss) 2.2 Background is yellow | ○ |  | Cuong Bui | 2024-04-12 | OK
IT | IT-SS-4-3-5 | 4 |  | 3 |  | 5 | Release from hold | 1. Continue with IT-SS-4-3-4 | 1. On GC click「保留解除」 button 2. View FreeSeat Layout | 2.1.Control's text is shown as below: - Seat number: SeatName - User name: 野澤 直紀 - Status: 着信通話 - Time: total time from logged in timing (format: hh:mm:ss) 2.2 Background is red | ○ |  | Cuong Bui | 2024-04-12 | OK
IT | IT-SS-4-3-6 | 4 |  | 3 |  | 6 | Disconnect incoming external call | 1. Continue with IT-SS-4-3-5 | 1. On GC click「電話を切る」 button 2. View FreeSeat Layout | 2.1.Control's text is shown as below: - Seat number: SeatName - User name: 野澤 直紀 - Status: アフターワーク中 - Time: total time from logged in timing (format: hh:mm:ss) 2.2 Background is light blue | ○ |  | Cuong Bui | 2024-04-12 | OK
IT | IT-SS-4-3-7 | 4 |  | 3 |  | 7 | ACW Done | 1. Continue with IT-SS-4-3-6 | 1. On GC click「Done」 button 2. View FreeSeat Layout | 2.1.Control's text is shown as below: - Seat number: SeatName - User name: 野澤 直紀 - Status: キュー中 - Time: total time from logged in timing (format: hh:mm:ss) 2.2 Background is light green | ○ |  | Cuong Bui | 2024-04-12 | OK
IT | IT-SS-4-4-1 | 4 |  | 4 | Inbound Call Status Reflect on multi layout - Manager account (View Mode) | 1 | On-Queue | 1. The following FreeSeat has been set on seatmap ・Site Name: FreeSeatSettingTest ・Layout: FreeSeat Layout ・FreeSeat: - FreeSeat1 - FreeSeat2 ・Site Name: FreeSeatSettingTest ・Layout: FreeSeat Layout2 ・FreeSeat: - FreeSeat1 2. Create Group [ToTest] 3. Setting Manager/ SV and OP as below Manager/SV: manager OP: 野澤 直紀 4. Mapping FreeSeat Layout and FreeSeat Layout2 with group [ToTest] 5. Logged in Map successfully by using manager account 6. Switch to view mode 7. On Operator Client login screen select [FreeSeatSettingTest > All layouts > FreeSeat1] and logged in successfully by 野澤 直紀 account | 1. On GC, set status to On Queue 2. View FreeSeat1 in Layout1 and Layout2 | 2.1.Control's text is shown as below: - Seat number: SeatName - User name: 野澤 直紀 - Status: キュー中 - Time: total time from logged in timing (format: hh:mm:ss) 2.2 Background is light green | ○ |  | Cuong Bui | 2024-04-12 | OK
IT | IT-SS-4-4-2 | 4 |  | 4 |  | 2 | Alerting | 1. Continue with IT-SS-4-4-1 | 1. On GC receive an incoming external call 2. View FreeSeat1 in Layout1 and Layout2 | 2.1.Control's text is shown as below: - Seat number: SeatName - User name: 野澤 直紀 - Status: 着信通話 - Time: total time from logged in timing (format: hh:mm:ss) 2.2 Background is red | ○ |  | Cuong Bui | 2024-04-12 | OK
IT | IT-SS-4-4-3 | 4 |  | 4 |  | 3 | Answer incoming external call | 1. Continue with IT-SS-4-4-2 | 1. On GC answer an incoming external call 2. View FreeSeat1 in Layout1 and Layout2 | 2.1.Control's text is shown as below: - Seat number: SeatName - User name: 野澤 直紀 - Status: 着信通話 - Time: total time from logged in timing (format: hh:mm:ss) 2.2 Background is red | ○ |  | Cuong Bui | 2024-04-12 | OK
IT | IT-SS-4-4-4 | 4 |  | 4 |  | 4 | On-Hold | 1. Continue with IT-SS-4-4-3 | 1. On GC click「保留」 button 2. View FreeSeat1 in Layout1 and Layout2 | 2.1.Control's text is shown as below: - Seat number: SeatName - User name: 野澤 直紀 - Status: 保留 - Time: total time from logged in timing (format: hh:mm:ss) 2.2 Background is yellow | ○ |  | Cuong Bui | 2024-04-12 | OK
IT | IT-SS-4-4-5 | 4 |  | 4 |  | 5 | Release from hold | 1. Continue with IT-SS-4-4-4 | 1. On GC click「保留解除」 button 2. View FreeSeat Layout | 2.1.Control's text is shown as below: - Seat number: SeatName - User name: 野澤 直紀 - Status: 着信通話 - Time: total time from logged in timing (format: hh:mm:ss) 2.2 Background is red | ○ |  | Cuong Bui | 2024-04-12 | OK
IT | IT-SS-4-4-6 | 4 |  | 4 |  | 6 | Disconnect incoming external call | 1. Continue with IT-SS-4-4-5 | 1. On GC click「電話を切る」 button 2. View FreeSeat1 in Layout1 and Layout2 | 2.1.Control's text is shown as below: - Seat number: SeatName - User name: 野澤 直紀 - Status: アフターワーク中 - Time: total time from logged in timing (format: hh:mm:ss) 2.2 Background is light blue | ○ |  | Cuong Bui | 2024-04-12 | OK
IT | IT-SS-4-4-7 | 4 |  | 4 |  | 7 | ACW Done | 1. Continue with IT-SS-4-4-6 | 1. On GC click「Done」 button 2. View FreeSeat1 in Layout1 and Layout2 | 2.1.Control's text is shown as below: - Seat number: SeatName - User name: 野澤 直紀 - Status: キュー中 - Time: total time from logged in timing (format: hh:mm:ss) 2.2 Background is light green | ○ |  | Cuong Bui | 2024-04-12 | OK
IT | IT-SS-4-5-1 | 4 |  | 5 | Inbound Call Status Reflect on multi layout - Supervisor account | 1 | On-Queue | 1. The following FreeSeat has been set on seatmap ・Site Name: FreeSeatSettingTest ・Layout: FreeSeat Layout ・FreeSeat: - FreeSeat1 - FreeSeat2 ・Site Name: FreeSeatSettingTest ・Layout: FreeSeat Layout2 ・FreeSeat: - FreeSeat1 2. Create Group [ToTest] 3. Setting Manager/ SV and OP as below Manager/SV: supervisor OP: 野澤 直紀 4. Mapping FreeSeat Layout and FreeSeat Layout2 with group [ToTest] 5. Logged in Map successfully by using supervisor account 6. On Operator Client login screen select [FreeSeatSettingTest > All layouts > FreeSeat1] and logged in successfully by 野澤 直紀 account | 1. On GC, set status to On Queue 2. View FreeSeat1 in Layout1 and Layout2 | 2.1.Control's text is shown as below: - Seat number: SeatName - User name: 野澤 直紀 - Status: キュー中 - Time: total time from logged in timing (format: hh:mm:ss) 2.2 Background is light green | ○ |  | Cuong Bui | 2024-04-12 | OK
IT | IT-SS-4-5-2 | 4 |  | 5 |  | 2 | Alerting | 1. Continue with IT-SS-4-5-1 | 1. On GC receive an incoming external call 2. View FreeSeat1 in Layout1 and Layout2 | 2.1.Control's text is shown as below: - Seat number: SeatName - User name: 野澤 直紀 - Status: アラーティング - Time: total time from logged in timing (format: hh:mm:ss) 2.2 Background is red | ○ |  | Cuong Bui | 2024-04-12 | OK
IT | IT-SS-4-5-3 | 4 |  | 5 |  | 3 | Answer incoming external call | 1. Continue with IT-SS-4-5-2 | 1. On GC answer an incoming external call 2. View FreeSeat1 in Layout1 and Layout2 | 2.1.Control's text is shown as below: - Seat number: SeatName - User name: 野澤 直紀 - Status: 着信通話 - Time: total time from logged in timing (format: hh:mm:ss) 2.2 Background is red | ○ |  | Cuong Bui | 2024-04-12 | OK
IT | IT-SS-4-5-4 | 4 |  | 5 |  | 4 | On-Hold | 1. Continue with IT-SS-4-5-3 | 1. On GC click「保留」 button 2. View FreeSeat1 in Layout1 and Layout2 | 2.1.Control's text is shown as below: - Seat number: SeatName - User name: 野澤 直紀 - Status: 保留 - Time: total time from logged in timing (format: hh:mm:ss) 2.2 Background is yellow | ○ |  | Cuong Bui | 2024-04-12 | OK
IT | IT-SS-4-5-5 | 4 |  | 5 |  | 5 | Release from hold | 1. Continue with IT-SS-4-5-4 | 1. On GC click「保留解除」 button 2. View FreeSeat Layout | 2.1.Control's text is shown as below: - Seat number: SeatName - User name: 野澤 直紀 - Status: 着信通話 - Time: total time from logged in timing (format: hh:mm:ss) 2.2 Background is red | ○ |  | Cuong Bui | 2024-04-12 | OK
IT | IT-SS-4-5-6 | 4 |  | 5 |  | 6 | Disconnect incoming external call | 1. Continue with IT-SS-4-5-5 | 1. On GC click「電話を切る」 button 2. View FreeSeat1 in Layout1 and Layout2 | 2.1.Control's text is shown as below: - Seat number: SeatName - User name: 野澤 直紀 - Status: アフターワーク中 - Time: total time from logged in timing (format: hh:mm:ss) 2.2 Background is light blue | ○ |  | Cuong Bui | 2024-04-12 | OK
IT | IT-SS-4-5-7 | 4 |  | 5 |  | 7 | ACW Done | 1. Continue with IT-SS-4-5-6 | 1. On GC click「Done」 button 2. View FreeSeat1 in Layout1 and Layout2 | 2.1.Control's text is shown as below: - Seat number: SeatName - User name: 野澤 直紀 - Status: キュー中 - Time: total time from logged in timing (format: hh:mm:ss) 2.2 Background is light green | ○ |  | Cuong Bui | 2024-04-12 | OK
IT | IT-SS-4-6-1 | 4 |  | 6 | Outbound Call Status Reflect - Manager account (View Mode) | 1 | Answer by calling outside Outside call | 1. The following FreeSeat has been set on seatmap ・Site Name: FreeSeatSettingTest ・Layout: FreeSeat Layout ・FreeSeat: - FreeSeat1 - FreeSeat2 2. Create Group [ToTest] 3. Setting Manager/ SV and OP as below Manager/SV: manager OP: 野澤 直紀 4. Mapping FreeSeat Layout and FreeSeat Layout2 with group [ToTest] 5. Logged in Map successfully by using manager account 6. Switch to view mode 7. On Operator Client login screen select [FreeSeatSettingTest > FreeSeat1 > FreeSeat1] and logged in successfully by 野澤 直紀 account | 1. On GC call outside 2. View FreeSeat Layout | 2.1.Control's text is shown as below: - Seat number: SeatName - User name: 野澤 直紀 - Status: 着信通話 発信中 - Time: total time from logged in timing (format: hh:mm:ss) 2.2 Background is red purple | ○ |  | Cuong Bui | 2024-04-15 | OK
IT | IT-SS-4-6-2 | 4 |  | 6 |  | 2 | Answer by calling outside | 1. Continue with IT-SS-4-6-1 | 1. Customer accept the call 2. View FreeSeat Layout | 2.1.Control's text is shown as below: - Seat number: SeatName - User name: 野澤 直紀 - Status: 発信通話中 - Time: total time from logged in timing (format: hh:mm:ss) 2.2 Background is red | ○ |  | Cuong Bui | 2024-04-15 | OK
IT | IT-SS-4-6-3 | 4 |  | 6 |  | 3 | On-Hold | 1. Continue with IT-SS-4-6-2 | 1. On GC click「保留」 button 2. View FreeSeat Layout | 2.1.Control's text is shown as below: - Seat number: SeatName - User name: 野澤 直紀 - Status: 保留 - Time: total time from logged in timing (format: hh:mm:ss) 2.2 Background is yellow | ○ |  | Cuong Bui | 2024-04-15 | OK
IT | IT-SS-4-6-4 | 4 |  | 6 |  | 4 | Release from hold | 1. Continue with IT-SS-4-6-3 | 1. On GC click「保留解除」 button 2. View FreeSeat Layout | 2.1.Control's text is shown as below: - Seat number: SeatName - User name: 野澤 直紀 - Status: 着信通話 発信通話中 - Time: total time from logged in timing (format: hh:mm:ss) 2.2 Background is red | ○ |  | Cuong Bui | 2024-04-15 | OK
IT | IT-SS-4-6-5 | 4 |  | 6 |  | 5 | Disconnect incoming external call | 1. Continue with IT-SS-4-6-4 | 1. On GC click「電話を切る」 button 2. View FreeSeat Layout | 2.1.Control's text is shown as below: - Seat number: SeatName - User name: 野澤 直紀 - Status: アフターワーク中 - Time: total time from logged in timing (format: hh:mm:ss) 2.2 Background is light blue | ○ |  | Cuong Bui | 2024-04-15 | OK
IT | IT-SS-4-6-6 | 4 |  | 6 |  | 6 | ACW Done | 1. Continue with IT-SS-4-6-5 | 1. On GC click「Done」 button 2. View FreeSeat Layout | 2.1.Control's text is shown as below: - Seat number: SeatName - User name: 野澤 直紀 - Status: キュー中 - Time: total time from logged in timing (format: hh:mm:ss) 2.2 Background is light green | ○ |  | Cuong Bui | 2024-04-15 | OK
IT | IT-SS-4-7-1 | 4 |  | 7 | Outbound Call Status Reflect - Supervisor account | 1 | Answer by calling outside Outside call | 1. The following FreeSeat has been set on seatmap ・Site Name: FreeSeatSettingTest ・Layout: FreeSeat Layout ・FreeSeat: - FreeSeat1 - FreeSeat2 2. Create Group [ToTest] 3. Setting Manager/ SV and OP as below Manager/SV: supervisor account OP: 野澤 直紀 4. Mapping FreeSeat Layout and FreeSeat Layout2 with group [ToTest] 5. Logged in Map successfully by using supervisor account 6. On Operator Client login screen select [FreeSeatSettingTest > FreeSeat1 > FreeSeat1] and logged in successfully by 野澤 直紀 account | 1. On GC call outside 2. View FreeSeat Layout | 2.1.Control's text is shown as below: - Seat number: SeatName - User name: 野澤 直紀 - Status: 着信通話 発信中 - Time: total time from logged in timing (format: hh:mm:ss) 2.2 Background is red purple | ○ |  | Cuong Bui | 2024-04-15 | OK
IT | IT-SS-4-7-2 | 4 |  | 7 |  | 2 | Answer by calling outside | 1. Continue with IT-SS-4-7-1 | 1. Customer accept the call 2. View FreeSeat Layout | 2.1.Control's text is shown as below: - Seat number: SeatName - User name: 野澤 直紀 - Status: 発信通話中 - Time: total time from logged in timing (format: hh:mm:ss) 2.2 Background is yellow | ○ |  | Cuong Bui | 2024-04-15 | OK
IT | IT-SS-4-7-3 | 4 |  | 7 |  | 3 | On-Hold | 1. Continue with IT-SS-4-7-2 | 1. On GC click「保留」 button 2. View FreeSeat Layout | 2.1.Control's text is shown as below: - Seat number: SeatName - User name: 野澤 直紀 - Status: 保留 - Time: total time from logged in timing (format: hh:mm:ss) 2.2 Background is yellow | ○ |  | Cuong Bui | 2024-04-15 | OK
IT | IT-SS-4-7-4 | 4 |  | 7 |  | 4 | Release from hold | 1. Continue with IT-SS-4-7-3 | 1. On GC click「保留解除」 button 2. View FreeSeat Layout | 2.1.Control's text is shown as below: - Seat number: SeatName - User name: 野澤 直紀 - Status: 着信通話 - Time: total time from logged in timing (format: hh:mm:ss) 2.2 Background is red | ○ |  | Cuong Bui | 2024-04-15 | OK
IT | IT-SS-4-7-5 | 4 |  | 7 |  | 5 | Disconnect incoming external call | 1. Continue with IT-SS-4-7-4 | 1. On GC click「電話を切る」 button 2. View FreeSeat Layout | 2.1.Control's text is shown as below: - Seat number: SeatName - User name: 野澤 直紀 - Status: アフターワーク中 - Time: total time from logged in timing (format: hh:mm:ss) 2.2 Background is light blue | ○ |  | Cuong Bui | 2024-04-15 | OK
IT | IT-SS-4-7-6 | 4 |  | 7 |  | 6 | ACW Done | 1. Continue with IT-SS-4-7-5 | 1. On GC click「Done」 button 2. View FreeSeat Layout | 2.1.Control's text is shown as below: - Seat number: SeatName - User name: 野澤 直紀 - Status: キュー中 - Time: total time from logged in timing (format: hh:mm:ss) 2.2 Background is light green | ○ |  | Cuong Bui | 2024-04-15 | OK
IT | IT-SS-4-8-1 | 4 |  | 8 | Outbound Call Status Reflect on multi layout - Manager account (View Mode) | 1 | Answer by calling outside Outside call | 1. The following FreeSeat has been set on seatmap ・Site Name: FreeSeatSettingTest ・Layout: FreeSeat Layout ・FreeSeat: - FreeSeat1 - FreeSeat2 ・Site Name: FreeSeatSettingTest ・Layout: FreeSeat Layout2 ・FreeSeat: - FreeSeat1 2. Create Group [ToTest] 3. Setting Manager/ SV and OP as below Manager/SV: manager OP: 野澤 直紀 4. Mapping FreeSeat Layout and FreeSeat Layout2 with group [ToTest] 5. Logged in Map successfully by using manager account 6. Switch to view mode 7. On Operator Client login screen select [FreeSeatSettingTest > All layouts > FreeSeat1] and logged in successfully by 野澤 直紀 account | 1. On GC call outside 2. View FreeSeat1 in Layout1 and Layout2 | 2.1.Control's text is shown as below: - Seat number: SeatName - User name: 野澤 直紀 - Status: 着信通話 発信中 - Time: total time from logged in timing (format: hh:mm:ss) 2.2 Background is red purple | ○ |  | Cuong Bui | 2024-04-15 | OK
IT | IT-SS-4-8-2 | 4 |  | 8 |  | 2 | Answer by calling outside | 1. Continue with IT-SS-4-8-1 | 1. Customer accept the call 2. View FreeSeat Layout | 2.1.Control's text is shown as below: - Seat number: SeatName - User name: 野澤 直紀 - Status: 発信通話中 - Time: total time from logged in timing (format: hh:mm:ss) 2.2 Background is yellow | ○ |  | Cuong Bui | 2024-04-15 | OK
IT | IT-SS-4-8-3 | 4 |  | 8 |  | 3 | On-Hold | 1. Continue with IT-SS-4-8-2 | 1. On GC click「保留」 button 2. View FreeSeat1 in Layout1 and Layout2 | 2.1.Control's text is shown as below: - Seat number: SeatName - User name: 野澤 直紀 - Status: 保留 - Time: total time from logged in timing (format: hh:mm:ss) 2.2 Background is yellow | ○ |  | Cuong Bui | 2024-04-15 | OK
IT | IT-SS-4-8-4 | 4 |  | 8 |  | 4 | Release from hold | 1. Continue with IT-SS-4-8-3 | 1. On GC click「保留解除」 button 2. View FreeSeat1 in Layout1 and Layout2 | 2.1.Control's text is shown as below: - Seat number: SeatName - User name: 野澤 直紀 - Status: 着信通話 発信通話中 - Time: total time from logged in timing (format: hh:mm:ss) 2.2 Background is red | ○ |  | Cuong Bui | 2024-04-15 | OK
IT | IT-SS-4-8-5 | 4 |  | 8 |  | 5 | Disconnect incoming external call | 1. Continue with IT-SS-4-8-4 | 1. On GC click「電話を切る」 button 2. View FreeSeat1 in Layout1 and Layout2 | 2.1.Control's text is shown as below: - Seat number: SeatName - User name: 野澤 直紀 - Status: アフターワーク中 - Time: total time from logged in timing (format: hh:mm:ss) 2.2 Background is light blue | ○ |  | Cuong Bui | 2024-04-15 | OK
IT | IT-SS-4-8-6 | 4 |  | 8 |  | 6 | ACW Done | 1. Continue with IT-SS-4-8-5 | 1. On GC click「Done」 button 2. View FreeSeat1 in Layout1 and Layout2 | 2.1.Control's text is shown as below: - Seat number: SeatName - User name: 野澤 直紀 - Status: キュー中 - Time: total time from logged in timing (format: hh:mm:ss) 2.2 Background is light green | ○ |  | Cuong Bui | 2024-04-15 | OK
IT | IT-SS-4-9-1 | 4 |  | 9 | Outbound Call Status Reflect on multi layout - Supervisor account | 1 | Answer by calling outside Outside call | 1. The following FreeSeat has been set on seatmap ・Site Name: FreeSeatSettingTest ・Layout: FreeSeat Layout ・FreeSeat: - FreeSeat1 - FreeSeat2 ・Site Name: FreeSeatSettingTest ・Layout: FreeSeat Layout2 ・FreeSeat: - FreeSeat1 2. Create Group [ToTest] 3. Setting Manager/ SV and OP as below Manager/SV: supervisor account OP: 野澤 直紀 4. Mapping FreeSeat Layout and FreeSeat Layout2 with group [ToTest] 5. Logged in Map successfully by using supervisor account 6. Login into Cxone 7. Open Max app 8. On Operator Client login screen select [FreeSeatSettingTest > All layouts > FreeSeat1] Input Username that logged in CXone and logged in successfully | 1. On CXone call outside 2. View FreeSeat1 in Layout1 and Layout2 | 2.1.Control's text is shown as below: - Seat number: SeatName - User name: 野澤 直紀 - Status: OutboundContact - Time: total time from logged in timing (format: hh:mm:ss) 2.2 Background is black | ○ |  | Cuong Bui | 2024-04-15 | OK
IT | IT-SS-4-9-2 | 4 |  | 9 |  | 2 | Answer by calling outside | 1. Continue with IT-SS-4-9-1 | 1. Customer accept the call 2. View FreeSeat Layout | 2.1.Control's text is shown as below: - Seat number: SeatName - User name: 野澤 直紀 - Status: 発信通話中 - Time: total time from logged in timing (format: hh:mm:ss) 2.2 Background is yellow | ○ |  | Cuong Bui | 2024-04-15 | OK
IT | IT-SS-4-9-3 | 4 |  | 9 |  | 3 | On-Hold | 1. Continue with IT-SS-4-9-2 | 1. On CXone click「Hold」 button 2. View FreeSeat1 in Layout1 and Layout2 | 2.1.Control's text is shown as below: - Seat number: SeatName - User name: 野澤 直紀 - Status: Hold - Time: total time from logged in timing (format: hh:mm:ss) 2.2 Background is black | ○ |  | Cuong Bui | 2024-04-15 | OK
IT | IT-SS-4-9-4 | 4 |  | 9 |  | 4 | Release from hold | 1. Continue with IT-SS-4-9-3 | 1. On CXone click「Unhold」 button 2. View FreeSeat1 in Layout1 and Layout2 | 2.1.Control's text is shown as below: - Seat number: SeatName - User name: 野澤 直紀 - Status: OutboundContact - Time: total time from logged in timing (format: hh:mm:ss) 2.2 Background is black | ○ |  | Cuong Bui | 2024-04-15 | OK
IT | IT-SS-4-9-5 | 4 |  | 9 |  | 5 | Disconnect incoming external call | 1. Continue with IT-SS-4-9-4 | 1. On CXone click「EndCall」 button 2. View FreeSeat1 in Layout1 and Layout2 | 2.1.Control's text is shown as below: - Seat number: SeatName - User name: 野澤 直紀 - Status: 後処理 - Time: total time from logged in timing (format: hh:mm:ss) 2.2 Background is black | ○ |  | Cuong Bui | 2024-04-15 | OK
IT | IT-SS-4-9-6 | 4 |  | 9 |  | 6 | ACW Done | 1. Continue with IT-SS-4-9-5 | 1. Wait 1 minute 2. View FreeSeat1 in Layout1 and Layout2 | 2.1.Control's text is shown as below: - Seat number: SeatName - User name: 野澤 直紀 - Status: Available - Time: total time from logged in timing (format: hh:mm:ss) 2.2 Background is light green | ○ |  | Cuong Bui | 2024-04-15 | OK
IT | IT-SS-4-10-1 | 4 |  | 10 | Freeseat logout | 1 | Confirm background color of layout is shown correctly when freeseat logout - Supervisor account | 1. The following FreeSeat has been set on seatmap ・Site Name: FreeSeatSettingTest ・Layout: FreeSeat Layout ・FreeSeat: - FreeSeat1 - FreeSeat2 2. Create Group [ToTest] 3. Setting Manager/ SV and OP as below Manager/SV: supervisor account OP: 野澤 直紀 4. Mapping FreeSeat Layout with group [ToTest] 5. Logged in Map successfully by using supervisor account 6. On Operator Client login screen select [FreeSeatSettingTest > FreeSeat Layout > FreeSeat2] and logged in successfully by 野澤 直紀 account | 1. Logout 野澤 直紀 2. View FreeSeat Layout | 2.1. Background of layout is gray | ○ |  | Hoang Nguyen
IT | IT-SS-4-10-2 | 4 |  | 10 |  | 2 | Confirm background color of layout is shown correctly when freeseat logout - Manager account (View Mode) | 1. The following FreeSeat has been set on seatmap ・Site Name: FreeSeatSettingTest ・Layout: FreeSeat Layout ・FreeSeat: - FreeSeat1 - FreeSeat2 2. Create Group [ToTest] 3. Setting Manager/ SV and OP as below Manager/SV: manager OP: 野澤 直紀 4. Mapping FreeSeat Layout with group [ToTest] 5. Logged in Map successfully by using manager account 6. Switch to view mode 7. On Operator Client login screen select [FreeSeatSettingTest > FreeSeat Layout > FreeSeat2] and logged in successfully by 野澤 直紀 account | 1. Logout 野澤 直紀 2. View FreeSeat Layout | 2.1. Background of layout is gray | ○ |  | Hoang Nguyen
IT | IT-SS-4-10-3 | 4 |  | 10 |  | 3 | Confirm text of all control of layout is shown correctly when freeseat logout - Supervisor account | 1. The following FreeSeat has been set on seatmap ・Site Name: FreeSeatSettingTest ・Layout: FreeSeat Layout ・FreeSeat: - FreeSeat1 - FreeSeat2 2. Create Group [ToTest] 3. Setting Manager/ SV and OP as below Manager/SV: supervisor OP: 野澤 直紀 4. Mapping FreeSeat Layout with group [ToTest] 5. Logged in Map successfully by using supervisor account 6. On Operator Client login screen select [FreeSeatSettingTest > FreeSeat Layout > FreeSeat2] and logged in successfully by 野澤 直紀 account | 1. Logout 野澤 直紀 2. View FreeSeat Layout | 2.1. Control's text is shown as below: - Seat number: SeatNumber - User name: - Status: - Time: | ○ |  | Hoang Nguyen
IT | IT-SS-4-10-4 | 4 |  | 10 |  | 4 | Confirm text of all control of layout is shown correctly when freeseat logout - Manager account (View Mode) | 1. The following FreeSeat has been set on seatmap ・Site Name: FreeSeatSettingTest ・Layout: FreeSeat Layout ・FreeSeat: - FreeSeat1 - FreeSeat2 2. Create Group [ToTest] 3. Setting Manager/ SV and OP as below Manager/SV: manager OP: 野澤 直紀 4. Mapping FreeSeat Layout with group [ToTest] 5. Logged in Map successfully by using manager account 6. Switch to view mode 7. On Operator Client login screen select [FreeSeatSettingTest > FreeSeat Layout > FreeSeat2] and logged in successfully by 野澤 直紀 account | 1. Logout 野澤 直紀 2. View FreeSeat Layout | 2.1. Control's text is shown as below: - Seat number: SeatNumber - User name: - Status: - Time: | ○ |  | Hoang Nguyen
IT | IT-SS-4-10-5 | 4 |  | 10 |  | 5 | Confirm menu popup on layout is disabled - Supervisor account | 1. The following FreeSeat has been set on seatmap ・Site Name: FreeSeatSettingTest ・Layout: FreeSeat Layout ・FreeSeat: - FreeSeat1 - FreeSeat2 2. Create Group [ToTest] 3. Setting Manager/ SV and OP as below Manager/SV: supervisor OP: 野澤 直紀 4. Mapping FreeSeat Layout with group [ToTest] 5. Logged in Map successfully by using supervisor account 6. On Operator Client login screen select [FreeSeatSettingTest > FreeSeat Layout > FreeSeat2] and logged in successfully by 野澤 直紀 account | 1. Logout 野澤 直紀 2. View FreeSeat Layout | 1.1/ Menu popup on layout by right click is disabled | ○ |  | Hoang Nguyen
IT | IT-SS-4-10-6 | 4 |  | 10 |  | 6 | Confirm menu popup on layout is disabled - Manager account (View Mode) | 1. The following FreeSeat has been set on seatmap ・Site Name: FreeSeatSettingTest ・Layout: FreeSeat Layout ・FreeSeat: - FreeSeat1 - FreeSeat2 2. Create Group [ToTest] 3. Setting Manager/ SV and OP as below Manager/SV: manager OP: 野澤 直紀 4. Mapping FreeSeat Layout with group [ToTest] 5. Logged in Map successfully by using manager account 6. Switch to view mode 7. On Operator Client login screen select [FreeSeatSettingTest > FreeSeat Layout > FreeSeat2] and logged in successfully by 野澤 直紀 account | 1. Logout 野澤 直紀 2. View FreeSeat Layout | 1.1/ Menu popup on layout by right click is disabled | ○ |  | Hoang Nguyen
IT | IT-SS-4-10-7 | 4 |  | 10 |  | 7 | Confirm multilayout is show correct - Supervisor account | 1. The following FreeSeat has been set on seatmap ・Site Name: FreeSeatSettingTest ・Layout: FreeSeat Layout ・FreeSeat: - FreeSeat1 - FreeSeat2 ・Site Name: FreeSeatSettingTest ・Layout: FreeSeat Layout2 ・FreeSeat: - FreeSeat1 2. Create Group [ToTest] 3. Setting Manager/ SV and OP as below Manager/SV: supervisor account OP: 野澤 直紀 4. Mapping FreeSeat Layout with group [ToTest] 5. Logged in Map successfully by using supervisor account 6. On Operator Client login screen select [FreeSeatSettingTest > All layouts > FreeSeat1] and logged in successfully by 野澤 直紀 account | 1. Logout 野澤 直紀 2. View FreeSeat Layout | 2.1/ FreeSeat1 in FreeSeat Layout and FreeSeat Layout2 are reflected - Background is gray - Control's Text: + Seat number: SeatNumber + User name: + Status: + Time: - Menu popup is disabled when right click on freeseat | ○ |  | Hoang Nguyen
IT | IT-SS-4-10-8 | 4 |  | 10 |  | 8 | Confirm multilayout is show correct - Manager account (View Mode) | 1. The following FreeSeat has been set on seatmap ・Site Name: FreeSeatSettingTest ・Layout: FreeSeat Layout ・FreeSeat: - FreeSeat1 - FreeSeat2 ・Site Name: FreeSeatSettingTest ・Layout: FreeSeat Layout2 ・FreeSeat: - FreeSeat1 2. Create Group [ToTest] 3. Setting Manager/ SV and OP as below Manager/SV: manager OP: 野澤 直紀 4. Mapping FreeSeat Layout with group [ToTest] 5. Logged in Map successfully by using manager account 6. Switch to view mode 7. On Operator Client login screen select [FreeSeatSettingTest > All layouts > FreeSeat1] and logged in successfully by 野澤 直紀 account | 1. Logout 野澤 直紀 2. View FreeSeat Layout | 2.1/ FreeSeat1 in FreeSeat Layout and FreeSeat Layout2 are reflected - Background is gray - Control's Text: + Seat number: SeatNumber + User name: + Status: + Time: - Menu popup is disabled when right click on freeseat | ○ |  | Hoang Nguyen
IT | IT-SS-5-1-1 | 5 | FixedSeat State | 1 | FixedSeat Create | 1 | Confirm control's text of fixed seat ís show correct - Supervisor account | 1. 1. The following FixedSeat has been set on seatmap ・Site Name: FreeSeatSettingTest ・Layout: FreeSeat Layout ・FixedSeat: - FixedSeat login by OP 野澤 直紀 2. Create Group [ToTest] 3. Setting Manager/ SV and OP as below Manager/SV: supervisor OP: 野澤 直紀 4. Mapping FreeSeat Layout with group [ToTest] 5. Logged in Map successfully by using supervisor account | 1. View FixedSeat Layout | 2.1. Control's text is shown as below: - User name: Username - Status: OP Status - Time: total time from logged in timing (format: hh:mm:ss) | ○ |  | Hoang Nguyen
IT | IT-SS-5-1-2 | 5 |  | 1 |  | 2 | Confirm control's text of fixed seat ís show correct - Manager account (View Mode) | 1. 1. The following FixedSeat has been set on seatmap ・Site Name: FreeSeatSettingTest ・Layout: FreeSeat Layout ・FixedSeat: - FixedSeat login by OP 野澤 直紀 2. Create Group [ToTest] 3. Setting Manager/ SV and OP as below Manager/SV: manager OP: 野澤 直紀 4. Mapping FreeSeat Layout with group [ToTest] 5. Logged in Map successfully by using manager account 6. Switch to view mode | 1. View FixedSeat Layout | 2.1. Control's text is shown as below: - User name: Username - Status: OP Status - Time: total time from logged in timing (format: hh:mm:ss) | ○ |  | Hoang Nguyen
IT | IT-SS-5-1-3 | 5 |  | 1 |  | 3 | Confirm background color of fixed seat is show correct - Supervisor account | 1. 1. The following FixedSeat has been set on seatmap ・Site Name: FreeSeatSettingTest ・Layout: FreeSeat Layout ・FixedSeat: - FixedSeat login by OP 野澤 直紀 2. Create Group [ToTest] 3. Setting Manager/ SV and OP as below Manager/SV: supervisor OP: 野澤 直紀 4. Mapping FreeSeat Layout with group [ToTest] 5. Logged in Map successfully by using supervisor account | 1. View FixedSeat Layout | 2.1/ Background color is green | ○ |  | Hoang Nguyen
IT | IT-SS-5-1-4 | 5 |  | 1 |  | 4 | Confirm background color of fixed seat is show correct - Manager account (View Mode) | 1. 1. The following FixedSeat has been set on seatmap ・Site Name: FreeSeatSettingTest ・Layout: FreeSeat Layout ・FixedSeat: - FixedSeat login by OP 野澤 直紀 2. Create Group [ToTest] 3. Setting Manager/ SV and OP as below Manager/SV: manager OP: 野澤 直紀 4. Mapping FreeSeat Layout with group [ToTest] 5. Logged in Map successfully by using manager account 6. Switch to view mode | 1. View FixedSeat Layout | 2.1/ Background color is green | ○ |  | Hoang Nguyen
IT | IT-SS-5-2-1 | 5 |  | 2 | FixedSeat Logout by OP logout | 1 | Confirm control's text of fixed seat ís show correct - Supervisor account | 1. The following FreeSeat and FixedSeat has been set on seatmap ・Site Name: FreeSeatSettingTest ・Layout: FreeSeat Layout ・FreedSeat: - FreeSeat1 ・FixedSeat: - FixedSeat login by OP 野澤 直紀 2. Create Group [ToTest] 3. Setting Manager/ SV and OP as below Manager/SV: supervisor OP: 野澤 直紀 4. Mapping FreeSeat Layout with group [ToTest] 5. Logged in Map successfully by using supervisor account | 1. Logout 野澤 直紀 2. View FixedSeat Layout | 2.1/ Text is white, Status is hidden, Elapsed time is fixed at 00:00:00 | ○ |  | Hoang Nguyen
IT | IT-SS-5-2-2 | 5 |  | 2 |  | 2 | Confirm control's text of fixed seat ís show correct - Manager account (View Mode) | 1. The following FreeSeat and FixedSeat has been set on seatmap ・Site Name: FreeSeatSettingTest ・Layout: FreeSeat Layout ・FreedSeat: - FreeSeat1 ・FixedSeat: - FixedSeat login by OP 野澤 直紀 2. Create Group [ToTest] 3. Setting Manager/ SV and OP as below Manager/SV: manager OP: 野澤 直紀 4. Mapping FreeSeat Layout with group [ToTest] 5. Logged in Map successfully by using manager account 6. Switch to view mode | 1. Logout 野澤 直紀 2. View FixedSeat Layout | 2.1/ Text is white, Status is hidden, Elapsed time is fixed at 00:00:00 | ○ |  | Hoang Nguyen
IT | IT-SS-5-2-3 | 5 |  | 2 |  | 3 | Confirm background color of fixed seat is show correct - Supervisor account | 1. The following FreeSeat and FixedSeat has been set on seatmap ・Site Name: FreeSeatSettingTest ・Layout: FreeSeat Layout ・FreedSeat: - FreeSeat1 ・FixedSeat: - FixedSeat login by OP 野澤 直紀 2. Create Group [ToTest] 3. Setting Manager/ SV and OP as below Manager/SV: supervisor account OP: 野澤 直紀 4. Mapping FreeSeat Layout with group [ToTest] 5. Logged in Map successfully by using supervisor account | 1. Logout 野澤 直紀 2. View FixedSeat Layout | 2.1/ Background color is black | ○ |  | Hoang Nguyen
IT | IT-SS-5-2-4 | 5 |  | 2 |  | 4 | Confirm background color of fixed seat is show correct - Manager account (View Mode) | 1. The following FreeSeat and FixedSeat has been set on seatmap ・Site Name: FreeSeatSettingTest ・Layout: FreeSeat Layout ・FreedSeat: - FreeSeat1 ・FixedSeat: - FixedSeat login by OP 野澤 直紀 2. Create Group [ToTest] 3. Setting Manager/ SV and OP as below Manager/SV: manager OP: 野澤 直紀 4. Mapping FreeSeat Layout with group [ToTest] 5. Logged in Map successfully by using manager account 6. Switch to view mode | 1. Logout 野澤 直紀 2. View FixedSeat Layout | 2.1/ Background color is black | ○ |  | Hoang Nguyen
IT | IT-SS-5-2-5 | 5 |  | 2 |  | 5 | Confirm menu popup on layout is disabled - Supervisor account | 1. The following FreeSeat and FixedSeat has been set on seatmap ・Site Name: FreeSeatSettingTest ・Layout: FreeSeat Layout ・FreedSeat: - FreeSeat1 ・FixedSeat: - FixedSeat login by OP 野澤 直紀 2. Create Group [ToTest] 3. Setting Manager/ SV and OP as below Manager/SV: supervisor account OP: 野澤 直紀 4. Mapping FreeSeat Layout with group [ToTest] 5. Logged in Map successfully by using supervisor account | 1. Logout 野澤 直紀 2. View FixedSeat Layout 3. Right click on FixedSeat layout | 3.1/ Menu popup on layout by right click is disabled | ○ |  | Hoang Nguyen
IT | IT-SS-5-2-6 | 5 |  | 2 |  | 6 | Confirm menu popup on layout is disabled - Manager account (View Mode) | 1. The following FreeSeat and FixedSeat has been set on seatmap ・Site Name: FreeSeatSettingTest ・Layout: FreeSeat Layout ・FreedSeat: - FreeSeat1 ・FixedSeat: - FixedSeat login by OP 野澤 直紀 2. Create Group [ToTest] 3. Setting Manager/ SV and OP as below Manager/SV: manager OP: 野澤 直紀 4. Mapping FreeSeat Layout with group [ToTest] 5. Logged in Map successfully by using manager account 6. Switch to view mode | 1. Logout 野澤 直紀 2. View FixedSeat Layout 3. Right click on FixedSeat layout | 3.1/ Menu popup on layout by right click is disabled | ○ |  | Hoang Nguyen
IT | IT-SS-5-3-1 | 5 |  | 3 | FixedSeat Logout by OP login to Freeseat | 1 | Confirm control's text of fixed seat ís show correct - Supervisor account | 1. The following FreeSeat and FixedSeat has been set on seatmap ・Site Name: FreeSeatSettingTest ・Layout: FreeSeat Layout ・FreedSeat: - FreeSeat1 ・FixedSeat: - FixedSeat login by OP 野澤 直紀 2. Create Group [ToTest] 3. Setting Manager/ SV and OP as below Manager/SV: supervisor OP: 野澤 直紀 4. Mapping FreeSeat Layout with group [ToTest] 5. Logged in Map successfully by using supervisor account | 1. On Operator Client login screen select [FreeSeatSettingTest > FreeSeat Layout > FreeSeat1] and logged in successfully by OP already in FixedSeat 2. View FixedSeat Layout 3. View FreeSeat Layout | 2.1/ Text is white, Status is hidden, Elapsed time is fixed at 00:00:00 3.1/ - Control's Text: + Seat number: SeatNumber + User name: OP Username + Status: OP Status + Time: total time from logged in timing (format: hh:mm:ss) | ○ |  | Hoang Nguyen
IT | IT-SS-5-3-2 | 5 |  | 3 |  | 2 | Confirm control's text of fixed seat ís show correct - Manager account (View Mode) | 1. The following FreeSeat and FixedSeat has been set on seatmap ・Site Name: FreeSeatSettingTest ・Layout: FreeSeat Layout ・FreedSeat: - FreeSeat1 ・FixedSeat: - FixedSeat login by OP 野澤 直紀 2. Create Group [ToTest] 3. Setting Manager/ SV and OP as below Manager/SV: manager OP: 野澤 直紀 4. Mapping FreeSeat Layout with group [ToTest] 5. Logged in Map successfully by using manager account 6. Switch to view mode | 1. On Operator Client login screen select [FreeSeatSettingTest > FreeSeat Layout > FreeSeat1] and logged in successfully by OP already in FixedSeat 2. View FixedSeat Layout 3. View FreeSeat Layout | 2.1/ Text is white, Status is hidden, Elapsed time is fixed at 00:00:00 3.1/ - Control's Text: + Seat number: SeatNumber + User name: OP Username + Status: OP Status + Time: total time from logged in timing (format: hh:mm:ss) | ○ |  | Hoang Nguyen
IT | IT-SS-5-3-3 | 5 |  | 3 |  | 3 | Confirm background color of fixed seat is show correct - Supervisor account | 1. The following FreeSeat and FixedSeat has been set on seatmap ・Site Name: FreeSeatSettingTest ・Layout: FreeSeat Layout ・FreedSeat: - FreeSeat1 ・FixedSeat: - FixedSeat login by OP 野澤 直紀 2. Create Group [ToTest] 3. Setting Manager/ SV and OP as below Manager/SV: supervisor account OP: 野澤 直紀 4. Mapping FreeSeat Layout with group [ToTest] 5. Logged in Map successfully by using supervisor account | 1. On Operator Client login screen select [FreeSeatSettingTest > FreeSeat Layout > FreeSeat1] and logged in successfully by OP already in FixedSeat 2. View FixedSeat Layout 3. View FreeSeat Layout | 2.1/ Background color is black 3.1/ Background color is green | ○ |  | Hoang Nguyen
IT | IT-SS-5-3-4 | 5 |  | 3 |  | 4 | Confirm background color of fixed seat is show correct - Manager account (View Mode) | 1. The following FreeSeat and FixedSeat has been set on seatmap ・Site Name: FreeSeatSettingTest ・Layout: FreeSeat Layout ・FreedSeat: - FreeSeat1 ・FixedSeat: - FixedSeat login by OP 野澤 直紀 2. Create Group [ToTest] 3. Setting Manager/ SV and OP as below Manager/SV: manager OP: 野澤 直紀 4. Mapping FreeSeat Layout with group [ToTest] 5. Logged in Map successfully by using manager account 6. Switch to view mode | 1. On Operator Client login screen select [FreeSeatSettingTest > FreeSeat Layout > FreeSeat1] and logged in successfully by OP already in FixedSeat 2. View FixedSeat Layout 3. View FreeSeat Layout | 2.1/ Background color is black 3.1/ Background color is green | ○ |  | Hoang Nguyen
IT | IT-SS-5-3-5 | 5 |  | 3 |  | 5 | Confirm menu popup on layout is disabled - Supervisor account | 1. The following FreeSeat and FixedSeat has been set on seatmap ・Site Name: FreeSeatSettingTest ・Layout: FreeSeat Layout ・FreedSeat: - FreeSeat1 ・FixedSeat: - FixedSeat login by OP 野澤 直紀 2. Create Group [ToTest] 3. Setting Manager/ SV and OP as below Manager/SV: supervisor account OP: 野澤 直紀 4. Mapping FreeSeat Layout with group [ToTest] 5. Logged in Map successfully by using supervisor account | 1. On Operator Client login screen select [FreeSeatSettingTest > FreeSeat Layout > FreeSeat1] and logged in successfully by OP already in FixedSeat 2. View FixedSeat Layout 3. Right click on FixedSeat layout 4. View FreeSeat Layout 5. Right click on FreeSeat layout | 3.1/ Menu popup on layout by right click is disabled 5.1/ Menu popup on layout by right click is shown | ○ |  | Hoang Nguyen
IT | IT-SS-5-3-6 | 5 |  | 3 |  | 6 | Confirm menu popup on layout is disabled - Manager account (View Mode) | 1. The following FreeSeat and FixedSeat has been set on seatmap ・Site Name: FreeSeatSettingTest ・Layout: FreeSeat Layout ・FreedSeat: - FreeSeat1 ・FixedSeat: - FixedSeat login by OP 野澤 直紀 2. Create Group [ToTest] 3. Setting Manager/ SV and OP as below Manager/SV: manager OP: 野澤 直紀 4. Mapping FreeSeat Layout with group [ToTest] 5. Logged in Map successfully by using manager account 6. Switch to view mode | 1. On Operator Client login screen select [FreeSeatSettingTest > FreeSeat Layout > FreeSeat1] and logged in successfully by OP already in FixedSeat 2. View FixedSeat Layout 3. Right click on FixedSeat layout 4. View FreeSeat Layout 5. Right click on FreeSeat layout | 3.1/ Menu popup on layout by right click is disabled 5.1/ Menu popup on layout by right click is shown | ○ |  | Hoang Nguyen
IT | IT-SS-5-4-1 | 5 |  | 4 | Operator login into freeseat before fixed seat is created | 1 | Confirm control's text of fixed seat ís show correct - Supervisor account | 1. The following FreeSeat has been set on seatmap ・Site Name: FreeSeatSettingTest ・Layout: FreeSeat Layout ・FreedSeat: - FreeSeat1 2. Create Group [ToTest] 3. Setting Manager/ SV and OP as below Manager/SV: supervisor account OP: 野澤 直紀 4. Mapping FreeSeat Layout with group [ToTest] 5. Logged in Map successfully by using supervisor account 6. On Operator Client login screen select [FreeSeatSettingTest > FreeSeat Layout > FreeSeat1] and logged in successfully by OP | 1. On Seatmap Screen select [FreeSeat Layout] and create a new FixedSeat by OP already logged in FreeSeat1 2. View FixedSeat Layout | 2.1/ Text is white, Status is hidden, Elapsed time is fixed at 00:00:00 | ○ |  | Hoang Nguyen
IT | IT-SS-5-4-2 | 5 |  | 4 |  | 2 | Confirm control's text of fixed seat ís show correct - Manager account (View Mode) | 1. The following FreeSeat has been set on seatmap ・Site Name: FreeSeatSettingTest ・Layout: FreeSeat Layout ・FreedSeat: - FreeSeat1 2. Create Group [ToTest] 3. Setting Manager/ SV and OP as below Manager/SV: manager OP: 野澤 直紀 4. Mapping FreeSeat Layout with group [ToTest] 5. Logged in Map successfully by using manager account 6. Switch to view mode 7.On Operator Client login screen select [FreeSeatSettingTest > FreeSeat Layout > FreeSeat1] and logged in successfully by OP | 1. On Seatmap Screen select [FreeSeat Layout] and create a new FixedSeat by OP already logged in FreeSeat1 2. View FixedSeat Layout | 2.1/ Text is white, Status is hidden, Elapsed time is fixed at 00:00:00 | ○ |  | Hoang Nguyen
IT | IT-SS-5-4-3 | 5 |  | 4 |  | 3 | Confirm background color of fixed seat is show correct - Supervisor account | 1. The following FreeSeat has been set on seatmap ・Site Name: FreeSeatSettingTest ・Layout: FreeSeat Layout ・FreedSeat: - FreeSeat1 2. Create Group [ToTest] 3. Setting Manager/ SV and OP as below Manager/SV: supervisor account OP: 野澤 直紀 4. Mapping FreeSeat Layout with group [ToTest] 5. Logged in Map successfully by using supervisor account 6. On Operator Client login screen select [FreeSeatSettingTest > FreeSeat Layout > FreeSeat1] and logged in successfully by OP | 1. On Seatmap Screen select [FreeSeat Layout] and create a new FixedSeat by OP already logged in FreeSeat1 2. View FixedSeat Layout | 2.1/ Background color is black | ○ |  | Hoang Nguyen
IT | IT-SS-5-4-4 | 5 |  | 4 |  | 4 | Confirm background color of fixed seat is show correct - Manager account (View Mode) | 1. The following FreeSeat has been set on seatmap ・Site Name: FreeSeatSettingTest ・Layout: FreeSeat Layout ・FreedSeat: - FreeSeat1 2. Create Group [ToTest] 3. Setting Manager/ SV and OP as below Manager/SV: manager OP: 野澤 直紀 4. Mapping FreeSeat Layout with group [ToTest] 5. Logged in Map successfully by using manager account 6. Switch to view mode 7.On Operator Client login screen select [FreeSeatSettingTest > FreeSeat Layout > FreeSeat1] and logged in successfully by OP | 1. On Seatmap Screen select [FreeSeat Layout] and create a new FixedSeat by OP already logged in FreeSeat1 2. View FixedSeat Layout | 2.1/ Background color is black | ○ |  | Hoang Nguyen
IT | IT-SS-5-4-5 | 5 |  | 4 |  | 5 | Confirm menu popup on layout is disabled - Supervisor account | 1. The following FreeSeat and FixedSeat has been set on seatmap ・Site Name: FreeSeatSettingTest ・Layout: FreeSeat Layout ・FreedSeat: - FreeSeat1 ・FixedSeat: - FixedSeat login by OP 野澤 直紀 2. Create Group [ToTest] 3. Setting Manager/ SV and OP as below Manager/SV: supervisor account OP: 野澤 直紀 4. Mapping FreeSeat Layout with group [ToTest] 5. Logged in Map successfully by using supervisor account | 1. On Seatmap Screen select [FreeSeat Layout] and create a new FixedSeat by OP already logged in FreeSeat1 2. View FixedSeat Layout 3. Right click on FixedSeat layout | 3.1/ Menu popup on layout by right click is disabled | ○ |  | Hoang Nguyen
IT | IT-SS-5-4-6 | 5 |  | 4 |  | 6 | Confirm menu popup on layout is disabled - Manager account (View Mode) | 1. The following FreeSeat and FixedSeat has been set on seatmap ・Site Name: FreeSeatSettingTest ・Layout: FreeSeat Layout ・FreedSeat: - FreeSeat1 ・FixedSeat: - FixedSeat login by OP 野澤 直紀 2. Create Group [ToTest] 3. Setting Manager/ SV and OP as below Manager/SV: manager OP: 野澤 直紀 4. Mapping FreeSeat Layout with group [ToTest] 5. Logged in Map successfully by using manager account 6. Switch to view mode | 1. On Seatmap Screen select [FreeSeat Layout] and create a new FixedSeat by OP already logged in FreeSeat1 2. View FixedSeat Layout 3. Right click on FixedSeat layout | 3.1/ Menu popup on layout by right click is disabled | ○ |  | Hoang Nguyen

## Seatmap License
[12 empty] | Number of test items | 7 | OK | 0
[12 empty] | Not implemented | 7 | NG | 0
[12 empty] | Progress rate | 0% | NT | 0
工程 | ＮＯ | Test items | [5 empty] | Preconditions | Steps | Expected Results | 試験実施 有無 | Browser type | Test member | Test day | Test results | Questionnaire number | Retest member | Retest date | Retest result | Finished Day | Remarks
|  | Main category |  | Sub-category |  | Test Title
IT | IT-SL-1-1-1 | 1 | Seatmap License | 1 | Column of table operators_login_history | 1 | Table have all columns follow DD | 1.Table operators_login_history is created | 1. Check [operators_login_history] table in DB | 1.1.Column of table is following: - tenantId - operatorId - state - stateChangedAt - createdAt | ○ |  | Tien Tran
IT | IT-SL-1-2-1 | 1 |  | 2 | Column of table seats_history | 1 | Table have all columns follow DD | 1.Table seats_history is created | 1. Check [seats_history] table in DB | 1.1.Column of table is following: - tenantId - siteId - siteName - layoutId - layoutName - seatId - seatName - operatorId - operatorName - createdAt | ○ |  | Tien Tran
IT | IT-SL-1-3-1 | 1 |  | 3 | Save Result into operators_login_history | 1 | Save success | 1. The following FreeSeat has been set on seatmap ・Site Name: FreeSeatSettingTest ・Layout: FreeSeat Layout ・FreeSeat: - FreeSeat1 - FreeSeat2 2. Create Group [LicenseTest] 3. Setting Manager/ SV and OP as below Manager/SV: manager OP: 野澤 直紀 4. Mapping FreeSeat Layout with group [LicenseTest] 5. Logged in Map successfully by using manager account 6. Switch to view mode 7. On Operator Client login screen select [FreeSeatSettingTest > FreeSeat Layout > FreeSeat2] and logged in successfully by 野澤 直紀 account | 1. Wait scheduled event execute 2. Check operators_login_history table in DB | 2.1 Confirm info login from operator is saved into operators_login_history table 2.2 Info login saved into table is matched with info login from operator and following: - tenantId - operatorId - state - stateChangedAt - createdAt | ○ |  | Tien Tran
IT | IT-SL-1-4-1 | 1 |  | 4 | Save Result into seats_history | 1 | Save success when seat is logged in | 1. The following FreeSeat has been set on seatmap ・Site Name: FreeSeatSettingTest ・Layout: FreeSeat Layout ・FreeSeat: - FreeSeat1 - FreeSeat2 2. Create Group [LicenseTest] 3. Setting Manager/ SV and OP as below Manager/SV: manager OP: 野澤 直紀 4. Mapping FreeSeat Layout with group [ToTest] 5. Logged in Map successfully by using manager account 6. Switch to view mode 7. On Operator Client login screen select [FreeSeatSettingTest > FreeSeat Layout > FreeSeat2] and logged in successfully by 野澤 直紀 account | 1. Wait scheduled event execute 2. Check seats_history table in DB | 2.1 Confirm info login from seat is saved into seats_history table 2.2 Info seats saved into table is matched with info seats and following: - tenantId - siteId - siteName - layoutId - layoutName - seatId - seatName - operatorId - operatorName - createdAt | ○ |  | Tien Tran
IT | IT-SL-1-4-2 | 1 |  | 4 |  | 2 | Save success when seat is not logged in | 1. The following FreeSeat has been set on seatmap ・Site Name: FreeSeatSettingTest ・Layout: FreeSeat Layout ・FreeSeat: - FreeSeat1 - FreeSeat2 | 1. Wait scheduled event execute 2. Check seats_history table in DB | 1.1 Confirm info login from seat is saved into seats_history table 1.2 Info seats saved into table is matched with info seat and following: - tenantId - siteId - siteName - layoutId - layoutName - seatId - seatName - createdAt | ○ |  | Tien Tran
IT | IT-SL-1-5-1 | 1 |  | 5 | Remove Expired License | 1 | Remove license [operators_login_history] is expired | 1. Setting config on Amazon EventBridge (e.g 5 minutes) 2. Run SQL query to update createdAt column - 1 year | 1. Scheduled event is ran by config 2. Check operators_login_history table in DB | 1.1. Licenses have createdAt > config time is removed | ○ |  | Tien Tran
IT | IT-SL-1-5-2 | 1 |  | 5 |  | 2 | Remove license [seats_history] is expired | 1. Setting config on Amazon EventBridge (e.g 5 minutes) 2. Run SQL query to update createdAt column - 1 year | 1. Wait scheduled event execute 2. Check seats_history table in DB | 1.1. Licenses have createdAt > config time is removed | ○ |  | Tien Tran

## Wallboard License
[12 empty] | Number of test items | 4 | OK | 0
[12 empty] | Not implemented | 4 | NG | 0
[12 empty] | Progress rate | 0% | NT | 0
工程 | ＮＯ | Test items | [5 empty] | Preconditions | Steps | Expected Results | 試験実施 有無 | Browser type | Test member | Test day | Test results | Questionnaire number | Retest member | Retest date | Retest result | Finished Day | Remarks
|  | Main category |  | Sub-category |  | Test Title
IT | IT-WL-1-1-1 | 1 | Wallboard License | 1 | Column of table operators_login_history | 1 | Table have all columns follow DD | 1.Table operators_login_history is created | 1. Check [operators_login_history] table in DB | 1.1.Column of table is following: - tenantId - userId - state - stateChangedAt | ○ |  | Tien Tran
IT | IT-WL-1-2-1 | 1 |  | 2 | Save Result into operators_login_history | 1 | Save success when operator logged in | 1. The following FreeSeat has been set on seatmap ・Site Name: FreeSeatSettingTest ・Layout: FreeSeat Layout ・FreeSeat: - FreeSeat1 - FreeSeat2 | 1. On Operator Client login screen select [FreeSeatSettingTest > FreeSeat Layout > FreeSeat2] and logged in successfully by 野澤 直紀 account 2. Wait for GC send message | 2.1 Confirm info login from operator is saved into operators_login_history table 2.2 Info login saved into table is matched with info login from operator and following: - tenantId - userId - state - stateChangedAt | ○ |  | Tien Tran
IT | IT-WL-1-2-2 | 1 |  | 2 |  | 2 | Save success when operator logged out | 1. The following FreeSeat has been set on seatmap ・Site Name: FreeSeatSettingTest ・Layout: FreeSeat Layout ・FreeSeat: - FreeSeat1 - FreeSeat2 2. On Operator Client login screen select [FreeSeatSettingTest > FreeSeat Layout > FreeSeat2] and logged in successfully by 野澤 直紀 account | 1. Logged out successfully by 野澤 直紀 account 2. Wait for GC send message | 2.1 Confirm info login from operator is saved into operators_login_history table 2.2 Info login saved into table is matched with info login from operator and following: - tenantId - userId - state - stateChangedAt | ○ |  | Tien Tran
IT | IT-WL-1-3-1 | 1 |  | 3 | Remove Expired License | 1 | Remove Success | 1. Setting config on Amazon EventBridge (e.g 5 minutes) 2. Run SQL query to update stateChangedAt column - 1 year | 1. Wait scheduled event execute 2. Check [operator_login_history] table in DB | 1.1. Licenses have stateChangedAt > config time is removed | ○ |  | Tien Tran

## フリーシートユースケース
フリーシートユースケース
反映される座席
No | 操作者 |  | ログイン先の座席 |  |  | ケース概要 | 拠点A > 1F > 0101 | 拠点A > 1F > 0102 | 拠点A > 2F > 0101 | 拠点A > 2F > 0102 | 拠点B > 1F > 0101 | 拠点B > 1F > 0102 | 拠点B > 2F > 0101 | 拠点B > 2F > 0102
1 | 拠点A | OP | 拠点A | 1F | 0101 | 自身が所属する拠点の座席へログインする場合 A拠点所属OPの例 | ○ | × | × | × | × | × | × | ×
2 | 拠点A | OP | 拠点A | 1F | 0102 |  | × | ○ | × | × | × | × | × | ×
3 | 拠点A | OP | 拠点A | 2F | 0101 |  | × | × | ○ | × | × | × | × | ×
4 | 拠点A | OP | 拠点A | 2F | 0102 |  | × | × | × | ○ | × | × | × | ×
5 | 拠点A | OP | 拠点A | 全レイアウト | 0101 |  | ○ | × | ○ | × | × | × | × | ×
6 | 拠点A | OP | 拠点A | 全レイアウト | 0102 |  | × | ○ | × | ○ | × | × | × | ×
7 | 拠点A | OP | 拠点B | 1F | 0101 | 自身が所属しない拠点の座席へログインする場合 A拠点所属OPの例 | × | × | × | × | × ※1 | × | × | ×
8 | 拠点A | OP | 拠点B | 1F | 0102 |  | × | × | × | × | × | × ※1 | × | ×
9 | 拠点A | OP | 拠点B | 2F | 0101 |  | × | × | × | × | × | × | × ※2 | ×
10 | 拠点A | OP | 拠点B | 2F | 0102 |  | × | × | × | × | × | × | × | × ※2
11 | 拠点A | OP | 拠点B | 全レイアウト | 0101 |  | × | × | × | × | × ※1 | × | × ※2 | ×
12 | 拠点A | OP | 拠点B | 全レイアウト | 0102 |  | × | × | × | × | × | × ※1 | × | × ※2
13 | 拠点B | OP | 拠点B | 1F | 0101 | 自身が所属する拠点の座席へログインする場合 B拠点所属OPの例 | × | × | × | × | ○ | × | × | ×
14 | 拠点B | OP | 拠点B | 1F | 0102 |  | × | × | × | × | × | ○ | × | ×
15 | 拠点B | OP | 拠点B | 2F | 0101 |  | × | × | × | × | × | × | ○ | ×
16 | 拠点B | OP | 拠点B | 2F | 0102 |  | × | × | × | × | × | × | × | ○
17 | 拠点B | OP | 拠点B | 全レイアウト | 0101 |  | × | × | × | × | ○ | × | ○ | ×
18 | 拠点B | OP | 拠点B | 全レイアウト | 0102 |  | × | × | × | × | × | ○ | × | ○
19 | 拠点B | OP | 拠点A | 1F | 0101 | 自身が所属しない拠点の座席へログインする場合 B拠点所属OPの例 | × ※3 | × | × | × | × | × | × | ×
20 | 拠点B | OP | 拠点A | 1F | 0102 |  | × | × ※3 | × | × | × | × | × | ×
21 | 拠点B | OP | 拠点A | 2F | 0101 |  | × | × | × ※4 | × | × | × | × | ×
22 | 拠点B | OP | 拠点A | 2F | 0102 |  | × | × | × | × ※4 | × | × | × | ×
23 | 拠点B | OP | 拠点A | 全レイアウト | 0101 |  | × ※3 | × | × ※4 | × | × | × | × | ×
24 | 拠点B | OP | 拠点A | 全レイアウト | 0102 |  | × | × ※3 | × | × ※4 | × | × | × | ×
※1 | 拠点B > 1F に割り当てるグループに拠点Aのオペレータを割り当てない設定を行うことで閲覧制御を実現する（既存グループ設定機能）
※2 | 拠点B > 2F に割り当てるグループに拠点Aのオペレータを割り当てない設定を行うことで閲覧制御を実現する（既存グループ設定機能）
※3 | 拠点A > 1F に割り当てるグループに拠点Bのオペレータを割り当てない設定を行うことで閲覧制御を実現する（既存グループ設定機能）
※4 | 拠点A > 2F に割り当てるグループに拠点Bのオペレータを割り当てない設定を行うことで閲覧制御を実現する（既存グループ設定機能）
※5 | 拠点A > 1F, 拠点A > 2F, 拠点B > 1F, 拠点B > 2F に割り当てるグループに上位SVと拠点A, 拠点Bのすべてのオペレータを割り当てる設定を行うことで閲覧制御を実現する（既存グループ設定機能）
全体管理者も同様にすべての拠点のレイアウトを閲覧可能なグループを割り当てる